## Title Page
VA-170822-SAIC Modification No. 004 | Exhibit 2.4.1 Implementation Milestones
Exhibit 2.4.1 Implementation Milestones VA-170822-SAIC
COMMONWEALTH OF VIRGINIA VIRGINIA INFORMATION TECHNOLOGIES AGENCY (VITA) SUPPLY CHAIN MANAGEMENT DIVISION 11751 MEADOWVILLE LANE CHESTER, VIRGINIA 23836

## Overview
Overview
This Milestones Exhibit will allow VITA to better understand the key phases, events, and timing of the Supplier's plans.
The worksheet reflects the major events of Supplier's contract lifecycle, including the Implementation Plan for implementing the Services and ongoing programs for maintaining and updating the Services, with verifiable criteria for acceptance. Milestones reflect the key events indicated over the course of the Implementation Plan and the overall term of Supplier's agreement. The Milestones will align with other documents as appropriate.
The worksheet is not intended to be a detailed project plan, but rather a list of key milestone activities. The Supplier may add to or delete rows from the worksheet as necessary.
Definitions of Fields
Ref ID # | Unique identifier, to be used at Supplier's option, to tie to other documents (e.g., Implementation Plan, Solution, Critical Deliverables, etc.)
Milestone | Name of the milestone
Category | Name of a grouping of activities (e.g., Service Desk, security) - to be determined at Supplier's option.
Description | Description of the activities comprising the milestone
Dependencies on Other Milestones (Ref #) | Indicate the reference numbers of predecessor/dependent milestones to support the current milestone.
Dependencies (i.e., on Commonwealth or Incumbents) | Describe dependencies or expectations of the incumbent suppliers, VITA, agencies, etc. Dependencies marked with an asterisk are prerequisite to SAIC's performance of implementation activities.
Risk Mitigation Approach | Describe the risk mitgation approach for any issues with the dependencies indicated in the prior columns.
Acceptance Criteria | Description of Acceptance Criteria, which will indicate completion of the milestone.
Start Date (Comm +/- Months) | Date when the activity begins in support of the milestone, in Months relative to Commencement.
Due Date (Comm +/- Months) | Date when the milestone will be completed in Months relative to Commencement (i.e. +/- number of months). Fractional values of 0, .25, .5, or .75 may be used.

## Implementation Milestones
Ref # | Foundational, Implementation Modules and Commencement Activities | Implementation Milestones | Category | Description | Dependencies on Other Milestones (Ref #) | Dependencies (i.e., on Commonwealth or Incumbents) | Revised Acceptance Criteria | Risk Mitigation Approach | Start Date (Comm +/- Months) | Due Date (Comm +/- Months) | New Start Date (Comm +/- Months)2 | New Due Date (Comm +/- Months)2
1 | Implementation Foundation | Contract Award & Signature | Contract | Fully executed contract complete. | N/A | VITA - Contract Signed | Fully executed contractual documentation | N/A | -10 Months | -9 Months | -14 Months | -14 Months
1.01 | Implementation Foundation | Implementation Day 1 | Contract | Official start date of Implementation. | 1 | N/A | Formal notification from VITA of the date to kick off implementation activities | N/A | -9 Months | -9 Months | -12 Months | -12 Months
1.02 | Implementation Foundation | Implementation Kickoff Meeting | Implementation Management | Kickoff meeting to formally start Implementation activities. | 1.01 | • VITA – Stakeholders identified • VITA – Facility for meeting (@ VITA location) • VITA – Incumbent notified and informed of upcoming required engagement in Implementation activities | 1) Meeting scheduled with agreed agenda 2) Meeting conducted with appropriate stakeholders 3) Meeting minutes and actions documented and published, slides published 4) Meeting documentation approved by VITA | Risk: VITA delays meeting or VITA-required personnel are not available when required, delaying MSI service commencement. Mitigation: 1) Provide VITA with scheduling information and required participants as early as possible 2) Include slack time in schedule to allow rescheduling Kickoff meeting | -9 Months | -9 Months | -12 Months | -12 Months
1.02a | Implementation Foundation | Executive ITISP Kickoff Event | Implementation Management | Offsite session with VITA Executive leadership, MSI Solution Team and SAIC to: 1) Ensure complete understanding of MSI model, VITA roles and responsibilities and engagement with the MSI 2) Establish VITA stakeholder “buy in” 3) Develop a strategy and "themes" for educating employees and communicating throughout the Implementation | 1.01 | • VITA – Participation of VITA Executive team (Executive Directors and Directors) • VITA – Facility for meeting (@ offsite location) | 1) Session scheduled with agreed agenda 2) Session conducted with appropriate stakeholders 3) Session minutes and actions documented and published, slides published 4) Session documentation approved by VITA | Risk: Lack of VITA participation impacts the successful implementation of the MSI model as not all VITA personnel are fully educated on the solution structure, how to engage and the benefits of the new services Mitigation: 1) Provide VITA with scheduling information and required participants as early as possible 2) Clearly articulate the value of the Session | -9 Months | -8 Months | -12 Months | -8 Months
1.03 | Implementation Foundation | Implementation Plan Management | Implementation Management | Mutually agreed Project Plan finalized and baselined (ready for execution), including tasks depicting the development of all specified sections of the SMM and their associated completion dates. | 1.02 | • VITA/Agencies – Stakeholder engagement required • VITA/Agencies – Communication of calendar “conflicts” to team • VITA/Agencies – Reviews and approvals as required • Incumbent – POC identified and engaged • Incumbent – Communication of calendar “conflicts” to team • VITA - Provide specific input regarding incumbent Supplier staff to Support SAIC Team decisions related to retention • Incumbent – HR POC identified and provision of list of all impacted personnel and contact information • VITA/Agencies –Draft Project Guidelines Review | 1) Draft Implementation Plan submitted for review 2) Joint working sessions to revise, customize and iterate as required (with VITA, Agencies) 3) Plan updated (iterative as necessary) 4) Review assessment methodology for each module 5) Plan submitted for approval 6) Baseline Project Plan approved 7) SMM tasks outlining sections and associated release schedule approved | Risk: Incumbent-required personnel are not available when required, delaying MSI service commencement. Mitigation: 1) Provide VITA with information regarding incumbent-related participation and required data as early as possible 2) Report on disentanglement compliance and escalate issues through VITA (require participation) 3) Include slack time in schedule to allow rescheduling Knowledge Transfer 4) Hold regular progress metrics and tracking and capture adjustments during shadowing (observations of undocumented processes/tasks) 5) Regularly apprise VITA of issues and request assistance to resolve them, as needed 6) Implement the Communication Strategy elements related to the incumbent contractor 7) Resolve issues collaboratively and expeditiously 8) Minimize requirements and expectations of incumbent to provide VITA-owned data and execution of existing contract responsibilities during implementation (e.g., change management) Risk: Incumbent personnel do not participate in Project planning efforts, resulting in delays in execution of project tasks due to schedule conflicts, missed activities, and additional work effort for the MSI Mitigation: 1) Provide VITA with information regarding incumbent-related participation and required data as early as possible 2) Report on disentanglement compliance and escalate issues through VITA (require participation) 3) Include slack time in schedule to allow rescheduling of activities dependent on incumbent personnel. Risk: Incumbent does not identify HR POC to facilitate communication with impacted employees and/or does not distribute communications in a timely manner and as a result, impacted employees are not aware of potential employment opportunities with SAIC so find employment elsewhere (leave early). Mitigation: 1) Communicate with NG early to ensure they are aware that SAIC will provide employment opportunities for impacted NG personnel 2) Report on disentanglement and escalate issues to ensure incumbent participates in HR discussions and distributes provided communications materials 3) VITA and SAIC develop alternative methodology for communicating with impacted employees in a timely manner such as LinkedIn messaging. Risk: VITA does not complete reviews of draft documents (Project Guidelines) or SMS dashboards in accordance with the agreed to schedule. Mitigation: 1) Ensure there is clear agreement with MSI and VITA on schedule and required staff for necessary reviews and that it is communicated to affected staff 2) Persistent interaction with VITA personnel in the development of all draft documents and interfaces. | -9 Months | -8 Months | -12 Months | -11 Months
1.04 | Implementation Foundation | Implementation Communications | Implementation Management | Mutually agreed Communications Plan finalized and baselined (ready for execution). | 1.02 | • VITA/Agencies – Participation in development of comprehensive Communications Matrix (Who, What, When, How) • VITA/Agencies – Delivery of communications to Commonwealth employees • Incumbent – Delivery of SAIC communications to impacted incumbent personnel | 1) Draft Communications Plan submitted for review 2) Joint working session to develop "external" Communications matrix (What, To Whom, When, How) - iterate as required 3) Implementation Project Communications matrix working session - iterate as required 4) Revised Communications Plan submitted 5) Communications Plan, Baseline External Communications Matrix and Project Communications Matrix approved | Risk: The absence of VITA involvement can lead to a misalignment of expectations and therefore delays due to rework. Mitigation: Close and persistent interaction with VITA personnel in the development and execution of the Communications Plan Risk: Communications are not delivered to the appropriate parties at the appropriate time, potentially impacting the “adoption rate” and perceived benefits and success of the new MSI services. Mitigation: Ensure VITA and Agency personnel are clear on their responsibilities for delivery of communications and monitor via Project status and Governance processes | -9 Months | -8 Months | -12 Months | -11 Months
1.04a | Implementation Foundation | Implementation Organizational Change Management (OCM) Communications | Implementation Management | Mutually agreed OCM Plan finalized and baselined (ready for execution). | 1.02, 1.04 | • VITA/Agencies – Participation in development of comprehensive OCM matrix (Who, What, When, How) • VITA/Agencies – Identification of pain points and areas of concern regarding MSI implementation (by Agency) so OCM can be targeted effectively • VITA/Agencies – Delivery of communications to Commonwealth employees | 1) Draft OCM Plan submitted for review 2) Joint working session to develop OCM matrix (What, To Whom, When, How) - iterate as required 3) Implementation Project OCM Communications matrix working session - iterate as required 4) Revised OCM Plan submitted 5) OCM Plan, Baseline OCM Matrix approved | Risk: The absence of VITA involvement can lead to a misalignment of expectations and therefore delays due to rework. Mitigation: Close and persistent interaction with VITA personnel in the development and execution of the OCM Plan Risk: Agency pain points and concerns are not appropriately identified (by Agency) so OCM plan is not effective managing change within a given Agency Mitigation: Ensure VITA and Agency participation in development of plan and identification of areas of concern Risk: Communications are not delivered to the appropriate parties at the appropriate time, potentially impacting the “adoption rate” and perceived benefits and success of the new MSI services. Mitigation: Ensure VITA and Agency personnel are clear on their responsibilities for delivery of communications and monitor via Project status and Governance processes | -9 Months | -8 Months | -12 Months | -9 Months
1.05 | Implementation Foundation | Implementation Risk Management | Implementation Management | Mutually agreed Risk Plan and Risk Register finalized and baselined (ready for execution). | 1.02 | • VITA/Agencies – Participation in initial Risk Workshop • VITA/Agencies – Ongoing reviews and approvals as required • VITA/Agencies – Assistance with escalations and implementation of agreed Mitigations if required • VITA/Agencies – Communications to appropriate Commonwealth management as required | 1) Draft Risk Plan submitted for review 2) Joint working session to develop Risk Register - iterate as required 3) Revised Risk Plan submitted 4) Risk Plan and Baseline Risk Register approved | Risk: The absence of VITA and Agency involvement can lead to a misalignment of expectations and potential unidentified Risk that could be realized and impact the Program. Mitigation: 1) Close and persistent interaction with VITA and Agency personnel in the development and execution of the Risk Register 2) Monitor Risk Register on a bi-weekly basis in Project status meetings to allow for ongoing input and updates | -9 Months | -8 Months | -12 Months | -11 Months
1.06 | Implementation Foundation | Implementation Quality Management | Implementation Management | SAIC Quality Plan finalized and baselined (ready for execution). | 1.02 | • VITA/Agencies – Review and approvals as necessary | 1) Draft Quality Assurance Management Plan submitted 2) Joint review of QA Plan conducted 3) Revised QA Plan submitted for approval 4) Baseline QA Plan approved | Risk: The absence of VITA involvement can lead to a misalignment of expectations and therefore delays due to rework. Mitigation: 1) Close and persistent interaction with VITA quality personnel 2) Escalation of baseline review to VITA Executive Management if more than 30 day delay | -9 Months | -8 Months | -12 Months | -11 Months
1.07 | Implementation Foundation | Initial Staffing | Staffing | Key management and technical personnel required for Implementation are available and fully engaged in Implementation activities. | 1 | • *VITA/Agencies – Provision of any staff onboarding requirements to SAIC early enough to allow for sufficient time to complete any required checks • VITA/Agencies – Provision of access to all required systems approved and completed • VITA/Agencies – Access to COVA and Agency facilities for SAIC Technical staff and BRMs • VITA/Agencies – VITA provides and PMs attend mandatory COVA PM training IAW R144 | 1) Formal notification to VITA that core team is in place and fully engaged and executing Implementation activities 2) SMM procedures updated and approved by VITA | Risk: VITA does not provide “background check” requirements early enough to allow for their completion prior to Implementation Kick off Mitigation: 1) VITA to provides requirements immediately following intent to award notification 2) Discuss potential of “waiver” to allow for initial planning work and activities to proceed while clearance requirements are being finalized. | -9 Months | -8 months | -12 Months | -11 Months
1.08 | Implementation Foundation | Facilities Buildout #1 | Facilities | SAIC MSI Program Office Facility (Richmond) - Offices Available | 1 | • VITA – Space requirements • *VITA/Incumbent – Technical assistance with network connectivity to VITA infrastructure (extension of network to facility, firewall configurations, security requirements, etc.) | 1) Space Requirements reviewed/accepted by VITA 2) Occupancy Permit Obtained 3) Richmond facility established and available for implementation activities 4) Richmond facility for VITA and SAIC implementation personnel meets VITA-provided requirements and is ready for occupancy | Risk: Availability may be delayed based on availability of supporting infrastructure. Mitigation: 1) Leverage long-standing relationships with infrastructure vendors 2) Engage SAIC Corporate Facilities department early 3) Conduct early communications regarding schedule 4) Ensure VITA network and security personnel engaged early to assist with establishment of required network connectivity Risk: VITA changes requirements for office space within SAIC facility and SAIC is delayed or unable to provide for modifications Mitigation: Request SAIC Corporate Facilities department ensure there is flexibility within the facility in terms of space etc. and understand the timing required to accommodate changes | -9 Months | -6 Months | -12 Months | -7 Months
1.09 | Implementation Foundation | SMS Standup | Operations - Tools | Core Service Management Systems (SMS) installed and operational, ready for Commonwealth specific configuration and customization. Please note: Should the Commonwealth direct that full commencement of MSI services be extended beyond our proposed target, SAIC may defer standup of selected SMS components to more closely align with the commencement of service on which they rely. | 1.03, 1.07 | • *VITA/Incumbent – Technical assistance with network connectivity to VITA infrastructure (extension of network to facility, firewall configurations, security requirements, etc.) • VITA/Incumbent/STS Service Management Staff – Access to required systems approved and provisioned (e.g. Active Directory) • VITA MSI Service Lead – Required infrastructure provisioned, configured and handed over to SAIC • VITA Service Desk Lead /Incumbent Service Desk Lead – “Configuration” data as required • VITA Security Architect/Agencies IT Managers/Incumbent Security Staff/STSs Security Staff – Required user account information • Incumbent - Establish appropriate technical interfaces and data feeds between SAIC tools and systems and Incumbent Supplier tools and systems | 1) SMS architecture document reviewed, and approved by VITA 2) SMS baseline tools acquired, installed (up and running), and pass agreed upon function testing 3) SMS baseline tools ready for configuration | Risk: Required infrastructure is not available within the VITA environment for the standup of the full suite of SAIC technical tools, delaying the overall implementation of MSI services Mitigation: SAIC and VITA mutually develop and agree on an alternative system architecture and deployment plan that satisfies all requirements and meets VITA security criteria. See additional information in Exhibit 2.4, Section 4, Fallback Scenario – Potential for Alternative Infrastructure Hosting | -9 Months | -5 Months | -12 Months | -6 Months
1.1 | Implementation Foundation | Critical Deliverables Plan | Implementation Management | SAIC Critical Deliverables Plan that lists the process by which critical deliverables will be accepted, and identifies the recurring and one-time critical deliverables. | 1.03, 1.07 | • VITA – Review and approvals as necessary | 1) Draft Critical Deliverables Plan submitted 2) Joint review of Critical Deliverables Plan conducted 3) Revised Critical Deliverables Plan submitted for approval 4) Baseline Critical Deliverables Plan approved 5) SMM procedures updated and approved by VITA | N/A | -6 Months | -4 Months | -6 Months | -4 Months
1.11 | Implementation Foundation | Facilities Buildout #2 | Facilities | SAIC Integrated Service Management Center (ISMC) Virginia Available | 1.00 | • *VITA/Incumbent – Technical assistance with network connectivity to VITA infrastructure (extension of network to facility, firewall configurations, security requirements, etc.) • VITA/Incumbent/STS - Access to required systems approved and provisioned | 1) Occupancy Permit Obtained 2) Clintwood facility secured and available for Service Desk implementation activities 3) VITA walk-thru of facility, confirming network connectivity and phone capability 4) Physical access controls confirmed 5) Rollover to TN facility successfully tested | Risk: Availability may be delayed based on availability of supporting infrastructure. Mitigation: 1) Leverage long-standing relationships with infrastructure vendors 2) Engage SAIC Corporate Facilities department early 3) Conduct early communications regarding schedule 4) Ensure VITA network and security personnel engaged early to assist with establishment of required network connectivity | -8 Months | -3 Months | -8 Months | -2 Months
1.12 | Implementation Foundation | Facilities Buildout #3 | Facilities | SAIC MSI Program Office Facility (Richmond) - JOC Available | 1 | • *VITA/Incumbent – Technical assistance with network connectivity to VITA infrastructure (extension of network to facility, firewall configurations, security requirements, etc.) • VITA/Incumbent/STS - Access to required systems approved and provisioned | 1) Occupancy Permit Obtained 2) Richmond facility established and available for JOC implementation activities 3) VITA walk-thru of facility, confirming network connectivity and phone capability | Risk: Availability may be delayed based on availability of supporting infrastructure. Mitigation: 1) Leverage long-standing relationships with infrastructure vendors. 2) Engage SAIC Corporate Facilities department early. 3) Communicate schedule early. 4) Ensure VITA network and security personnel are engaged early to assist with establishment of required network connectivity. | -8 Months | -3 Months | -8 Months | -3 Months
1.13 | Implementation Foundation | Transition Out Plan | Implementation Management | Transition Out Plan that formally documents the process for the transition of the powers, duties, activities, and functions from Supplier to VITA. | 4.01, 8.04, 10.06 | • VITA – Review and approvals as necessary | 1) Draft Transition Out Plan submitted 2) Joint review of Transition Out Plan conducted 3) Revised Transition Out Plan submitted for approval 4) Baseline Transition Out Plan approved 5) SMM updated and approved by VITA | N/A | -3 Months | 0 Months | -3 Months | 0 Months
1.14 | Implementation Foundation | Implementation Foundation Baseline Timeframe Complete | Implementation Management | SAIC 9 month Implementation Foundation work completed |  | N/A | 1) 9 months elapsed 2) Implementation activities on track and all preceding Implementation Foundation milestones completed 3) Commencement Date not delayed due to SAIC | N/A | -9 Months | 0 Months | -12 Months | -4 Months
1.15 | Implementation Foundation | Implementation Complete | Implementation Management | VITA has provided confirmation that all Implementation activities have been successfully executed and that the MSI is fully operational. | 4.01, 8.04, 10.07 | N/A | 1) Formal closeout report/documentation issued 2) VITA approves and confirms that all Implementation activities have been executed 3) All milestones have been met or completed, acceptance test passed 4) Mutually agreed post commencement punch list (if required) has been approved by VITA 5) Post implementation monitoring / quality assurance approach developed | N/A | 0 Months | +3 Months | -3 Months | +4 Months
2 | DART | DART Kickoff | Implementation Management | SAIC Advisory team personnel are available and fully engaged to begin activities associated with implementation complexities and to create specialized management and governance structures associated with incumbent disentanglement activities | 1.02, 1.07 | • VITA – Stakeholders identified • VITA – Information regarding incumbent contracts, agreements etc. provided to SAIC for review • VITA – Incumbent informed of SAIC’s “role” • VITA – Provision of information regarding VITA communications and actions taken to date • VITA – Provision of timeline information and plans for upcoming procurements | 1) Meeting scheduled with agreed agenda 2) Meeting conducted with appropriate stakeholders 3) Meeting minutes and actions documented and published, slides published 4) Meeting documentation approved by VITA 5) Develop management team and governance structure to address incumbent disentanglement activities | Risk: Information from the Incumbent needed for disentanglement efforts has not yet been provided to VITA Mitigation: Provide VITA with list of artifacts to be reviewed as early as possible so they can begin collection of data | -9 Months | -9 Months | -12 Months | -11 Months
2.01 | DART | DART Planning Complete | Implementation Management | Advisory team and VITA personnel have agreed and finalized plan for activities, objectives and structure to be completed during the engagement | 2 | • VITA – Participation in prioritization of activities based on discovery of “what is possible” following contract analysis and conversations with incumbent • VITA – Reviews and approvals as required | 1) Disentanglement Advisory and Recommendation Team kickoff meeting conducted 2) Current contract terms and conditions reviewed and decomposed 3) Gap analysis completed 4) Functions for potential early implementation identified 5) Detailed disentanglement plan/schedule developed, delivered and approved | N/A | -9 Months | -7 months | -12 Months | -8 Months
3 | IT Financial Management | ITFM - Gap Analysis Complete | ITFM | Delivery of gap analysis and associated action plan for VITA IT Cost Management Framework and Processes | 1.03 | • VITA/Agencies – Timely access to key stakeholders for interviews • VITA/Agencies – Access to existing process and cost model documentation • VITA/Agencies – Access to data and data sources as requested" | 1) High level gap analysis for ITFM Governance, Invoicing/Chargeback, Cost Allocation, Forecasting/Budgeting, Disputes approved by VITA. 2) ITFM Roadmap for IT Cost Framework Definitions, Cost Management, and Cost Pool development approved by VITA. | Risk: VITA and Agency personnel are not available for interviews in a timely manner causing delays Mitigation: Provide interview list with schedule requirements during Week 1 Risk: Required documentation is not available in a timely manner causing delays Mitigation: Provide document and data request list during Week 1 | -9 Months | -8 Months | -12 Months | -8 Months
3.01 | IT Financial Management | ITFM - April Sprint Milestones | ITFM | Delivery of ITFM Governance, Deployment Plan, Cost Pools and Out-of-the-box Enterprise and Chargeback invoices | 3 | • VITA/Agencies – Participation from key Commonwealth stakeholders in ITFM workshops • VITA/Agencies – Timely validation of sprint planning activities | 1) ITFM Governance reviewed and approved by VITA, SAIC, and Agency stakeholders 2) ITFM Deployment Plan reviewed and approved by VITA, SAIC, and Agency stakeholders 3) ITFM Cost Pools reviewed and approved by VITA, SAIC, and Agency stakeholders 4) ITFM Out-of-the-box enterprise and chargeback invoices reviewed and approved by VITA, SAIC, and Agency stakeholders | Risk: VITA and Agency personnel are not available for workshops on scheduled dates requiring changes and elongating the overall schedule for implementation Mitigation: Provide guidance on most appropriate workshop participants. Provide schedule to workshop participants early and send reminders Risk: VITA and Agency personnel do not provide validation in a timely manner causing delays Mitigation: 1) Establish standard validation process for each process area 2) Ensure schedule is communicated to VITA/Agency personnel early and send reminders |  |  | -8 Months | -6 Months
3.02 | IT Financial Management | ITFM - May Sprint Milestones | ITFM | Delivery of ITFM Chargeback and Cost Allocation Process, Vendor Invoicing Process, Cost Allocation Model and Cost Framework Definitions | 3.01 | • VITA/Agencies – Participation from key Commonwealth stakeholders in ITFM workshops • VITA/Agencies – Timely validation of sprint planning activities | 1) ITFM Chargeback and Cost Allocation Process reviewed and approved by VITA, SAIC, and Agency stakeholders 2) ITFM Vendor Invocing Process reviewed and approved by VITA, SAIC, and Agency stakeholders 3) ITFM Cost allocation model and cost framework definitions reviewed and approved by VITA, SAIC, and Agency stakeholders. | Risk: VITA and Agency personnel are not available for workshops on scheduled dates requiring changes and elongating the overall schedule for implementation Mitigation: Provide guidance on most appropriate workshop participants. Provide schedule to workshop participants early and send reminders Risk: VITA and Agency personnel do not provide validation in a timely manner causing delays Mitigation: 1) Establish standard validation process for each process area 2) Ensure schedule is communicated to VITA/Agency personnel early and send reminders |  |  | -6 Months | -5 Months
3.03 | IT Financial Management | ITFM - June Sprint Milestones | ITFM | Delivery of ITFM forecasting and budgeting process | 3.02 | • VITA/Agencies – Participation from key Commonwealth stakeholders in ITFM workshops • VITA/Agencies – Timely validation of sprint planning activities | 1) ITFM forecasting and budgeting process reviewed and approved by VITA, SAIC, and Agency stakeholders | Risk: VITA and Agency personnel are not available for workshops on scheduled dates requiring changes and elongating the overall schedule for implementation Mitigation: Provide guidance on most appropriate workshop participants. Provide schedule to workshop participants early and send reminders Risk: VITA and Agency personnel do not provide validation in a timely manner causing delays Mitigation: 1) Establish standard validation process for each process area 2) Ensure schedule is communicated to VITA/Agency personnel early and send reminders |  |  | -5 Months | -4 Months
3.04 | IT Financial Management | ITFM - July Sprint Milestones | ITFM | Delivery of ITFM Tool Configuration and Reporting requirements and Dispute Process | 3.03 | • VITA/Agencies – Participation from key Commonwealth stakeholders in ITFM workshops • VITA/Agencies – Timely validation of sprint planning activities | 1) ITFM Tool configuration and reporting requirements reviewed, validated, approved by approved by VITA, SAIC and Agency stakeholders 2) ITFM Dispute Process reviewed and approved by VITA, SAIC and Agency stakeholders | Risk: VITA and Agency personnel are not available for workshops on scheduled dates requiring changes and elongating the overall schedule for implementation Mitigation: Provide guidance on most appropriate workshop participants. Provide schedule to workshop participants early and send reminders Risk: VITA and Agency personnel do not provide validation in a timely manner causing delays Mitigation: 1) Establish standard validation process for each process area 2) Ensure schedule is communicated to VITA/Agency personnel early and send reminders |  |  | -4 Months | -3 Months
3.05 | IT Financial Management | ITFM - August Sprint Milestones | ITFM | Delivery of ITFM final Enterprise and Chargeback invoices, User Acceptance Test Summary and ITFM SMM Sections | 3.04 | • VITA/Agencies – Participation from key Commonwealth stakeholders in ITFM workshops • VITA/Agencies – Timely validation of sprint planning activities | 1) Updated Enterprise form of invoice and chargeback form of invoice reviewed and approved by VITA SAIC and Agency (via VITA) stakeholders. 2) UAT Test Plan and Cases completed and approved by VITA, SAIC and Agency (via VITA) stakeholders 3) ITFM SMM reviewed and approved by VITA | Risk: VITA and Agency personnel are not available for workshops on scheduled dates requiring changes and elongating the overall schedule for implementation Mitigation: Provide guidance on most appropriate workshop participants. Provide schedule to workshop participants early and send reminders Risk: VITA and Agency personnel do not provide validation in a timely manner causing delays Mitigation: 1) Establish standard validation process for each process area 2) Ensure schedule is communicated to VITA/Agency personnel early and send reminders |  |  | -3 Months | -2 Months
3.06 | IT Financial Management | IT Financial Management Implementation | ITFM | Integration of financial and accounting systems is complete. Service Chargeback accounting is fully operational as is budgeting and forecast analysis and reporting | 3.05, 10.01, 10.06 | • Incumbent – Availability for Knowledge Transfer sessions and provision of associated documentation • VITA/Incumbent – Provision of historical data for inclusion in tool configuration • VITA/Agencies – Availability for requirements clarification session • VITA/Agencies – Provision of required data for tool configuration (e.g. Cost centers, etc.) • VITA – Technical personnel to assist with integration of SAIC tools with VITA ERP/Financial systems • VITA/Agencies – Appropriate personnel are available for CRR activities and associated sign off | 1) ITFM toolset installed, configured and integrated with SMS toolset 2) Test documentation, showing that interfaces have been defined, work as predicted, and have been verified, delivered and approved 3) ITFM Implementation Readiness Plan (Training and Stakeholder Execution Plan), reviewed and approved by VITA 4) User acceptance testing, confirming that the operational system supporting all agreed aspects including capability for budgeting and forecasting, reporting, is complete. 5) Commencement Readiness Reviews reviewed and approved by VITA, SAIC and Agency representatives | Risk: Incumbent personnel are not available for knowledge transfer sessions and/or delay the provision of documentation causing a delay in implementation activities Mitigation: 1) Provide VITA with information regarding incumbent-related participation and required data as early as possible 2) Report on disentanglement compliance and escalate issues through VITA (require participation) 3) Include slack time in schedule to allow rescheduling Knowledge Transfer 4) Hold regular progress metrics and tracking and capture adjustments during shadowing (observations of undocumented processes/tasks) 5) Regularly apprise VITA of issues and request assistance to resolve them, as needed 6) Implement the Communication Strategy elements related to the incumbent contractor 7) Resolve issues collaboratively and expeditiously 8) Minimize requirements and expectations of incumbent to provide VITA-owned data and execution of existing contract responsibilities during implementation (e.g., change management) 9) Ensure VITA gains agreement for at a minimum job shadowing to allow SAIC to document ongoing operational processes and activities Risk: Technical personnel required to assist with integration of new ITFM systems to existing VITA financial systems are unavailable causing delays in the deployment of the new ITFM system Mitigation: Provide VITA with tool deployment plan as early as possible along with associated timeline for integrations so that resources can be identified and made available as required |  |  | -2 Months | 0 Months
3.07 | IT Financial Management | IT Financial Management Implementation | ITFM | Delivery of Cost Savings Opportunity process models and reports associated with ongoing ITFM operations | 3.06 | • VITA/Agencies – Participation from key Commonwealth stakeholders in design workshops • VITA/Agencies – Timely validation of process models and reports | 1) Cost Savings Opportunity process reviewed and approved by VITA and SAIC. | Risk: VITA and Agency personnel are not available for workshops on scheduled dates requiring changes and elongating the overall schedule Mitigation: Provide guidance on most appropriate workshop participants. Provide schedule to workshop participants early and send reminders Risk: VITA and Agency personnel do not provide validation in a timely manner causing delays Mitigation: 1) Establish standard validation process process area 2) Ensure schedule is communicated to VITA/Agency personnel early and send reminders |  |  | 0 Month | 0 Months
4 | Program Management Office | Program Management Office Stood Up | PMO | Basic Project Management support using currently available tools to provide guidance on projects including: o Communications support o Cross Project support o BRM support o Risk Management support o Proposal Development support Establishment of: o Reporting processes o SMM Repository and Documentation Management o Ongoing Programs Support and Maintenance process Collaboration with SMS and Portal Team to customize tools for VITA-grade project management and portfolio management support. * assumes 5 PMs and 4 support staff minimum | 1.07, 1.08, 1.09, 5.00, 6.00, 8.03, 11.00 | • VITA/Agencies/Incumbent – Project plans, data and status • VITA/Agencies – Up to date Exh 2.6 and underlying details • VITA/Agencies – Information on project meetings • VITA/Agencies – Report examples and schedule including data source information • VITA – SMM Documentation • VITA – Timely reviews from VITA • Agencies – Information on Agency PMs and Agency PMOs • Incumbent – Available for knowledge transfer (KT) and shadowing | 1) Draft PM Processes reviewed and approved feedback received from VITA stakeholder(s) 2) PMO providing status on projects in interim via agreed upon communications channels until SMS dashboards ready (scalable PM support) 3) Project risk management process complete and support in place 4) PMO accepting and supporting proposal development requests (scalable) 5) Develop reports (PM Performance, Quarterly Strategy Analysis, and Monthly & Weekly CSI) 6) Ongoing Programs process complete 7) PMO accepting and supporting Project requests (scalable) based upon mutually agreed to project selection and initiation process to include Project Charter. | Risk: Incumbent personnel are not available for knowledge transfer sessions and/or delay the provision of documentation causing a delay in implementation activities Mitigation: 1) Provide VITA and incumbent with information and required data as early as possible 2) Hold regular progress metrics and tracking and capture adjustments during shadowing (observations of undocumented processes/tasks) 3) Regularly apprise VITA of issues and request assistance to resolve them, as needed 4) Implement the Communication Strategy elements related to the incumbent contractor and try to resolve issues collaboratively and expeditiously 5) Minimize requirements and expectations of incumbent to provide VITA-owned data and execution of existing contract responsibilities during implementation (e.g., change management) 6) Ensure VITA gains agreement for job shadowing to allow SAIC to document ongoing operational processes and activities | -9 Months | -5 Months | -9 Months | -5 Months
4.01 | Program Office | Program Office Implementation | PMO | All Program Office functions are fully operational including: o Demand, Project, & Portfolio Management o Solution Request Management o Service Management Manual Maintenance o Ongoing Programs o STS Project Support including onboarding & offboarding o Project Tracking and Management via SMS o Service Transition support o Definition and documentation of relational and operational governance model, including all forums needed for Commencement completed | 4.00, 7.00, 7.01, 8.01, 9.00, 10.02 | • VITA/Agencies/Incumbent - Project Data and Status • VITA - STS Wave details • VITA/Agencies - Ongoing information on project meetings • VITA/Agencies - Ongoing information on VITA/Agency PMs and VITA/Agency PMOs • VITA - Timely reviews from VITA • Incumbent - identify and provide documentation regarding projects that are projected to be in process at Commencement | 1) Program/project management performed by PMO for applicable projects/programs outlined in Exhibit 2.1 - sections 2.1 and 2.2 2) Customer able to submit Demand Requests and they are properly routed and categorized 3) Project Portfolio Management functionally capable via SMS. Additional support for analysis and resource forecasting in place as outlined in Exhibit 2.1 - section 2.3 4) SMM fully supported 5) Ongoing Programs receiving support outlined in Exhibit 2.1 - section 2.4 6) Documentation of operational and relational governance model 7) Program Management Office (M4.00) Draft PM Processes revised to a Final state, based on learnings between June 2018 and September 2018; with feedback received from VITA stakeholders incorporated into the Final process documents 8) OLA's establilshed with each STS and signed off on | Risk: 1) VITA stakeholders may be uncertain about our readiness for operational assumption and be uncomfortable providing us with authority to proceed at the commencement for a given service area. 2) VITA does not have full documentation of ongoing projects, technical currency, improvement register, and/or Agency demand. Mitigation: 1) SAIC and VITA will discuss and agree on the readiness criteria that must be met prior to the commencement of services. 2) The SAIC Implementation Team will execute interim and final CRRs prior to each service commencement. 3) SAIC and VITA will review the readiness review approach, proposed schedule, and identified timing and adjust processes to meet VITA’s expectations. 4) BRM's working with CAM's go Agency to Agency with PMO and Architecture questionnaire to conduct interviews. Risk: Restarting PMO with new PMs may take longer than planned due to unfamiliarity with KE SMS. Mitigation: 1) Hire PMs that have working knowledge of ServiceNow | -4 Months | 0 Months | -4 Months | 0 Months
5 | Current State Assessments | ITIL Assessment | Operations - Process | ITIL process maturity assessment and gap analysis conducted and completed. | 1.03, 1.07 | • VITA/Agencies –Identification of key stakeholders and participation as requested (meetings, interviews, etc.) • VITA/Agencies – Provision of existing process documentation for the following service delivery areas: o Incident Management o Problem Management o Change Management o Release Management o Configuration Management o Other ITIL process areas as necessary • VITA – Notification to incumbent of assessment activities and required participation • Incumbent – Provision of “read” access and “walk through” of the current ITSM tool (to allow for process workflow analysis etc.) • VITA/Agencies – Provision of VITA/Agency approval structure for the following: o New service provision o Termination of existing service o Procurement of services o Budget planning o Invoice approval | 1) Review assessment methodology 2) Complete analysis of data for findings, process, procedures, etc. for current-state baseline 3) Presentation of Assessment findings and recommendations for improvement 4) Confirm the list of gaps to remediate, including identification of affected workstreams 5) VITA to approve and prioritize actions intended to resolve the identified gaps. | Risk: Information required to complete ITIL assessment is delayed. Mitigation: Inform VITA early of the information required to successfully perform this assessment Risk: Incumbent delays or denies “read” access to current ITSM tool set delaying assessment analysis activities Mitigation: 1) Inform incumbent of upcoming requirement as early as possible and gain concurrence for granting access 2) Ensure VITA personnel have required access so they could relay and/or demonstrate required information to SAIC personnel | -7 Months | -5 Months | -9 Months | -6 Months
5.01 | Current State Assessments | CyberSecurity Edge Assessment | Operations - Security | Cybersecurity Edge assessment to identify the current information security policy and baseline, compare the stated baseline against policy, requirements, and best practices and then develop and recommend plans of actions to achieve recommended future state. | 1.03, 1.07 | • VITA/Agencies Security Staff – Participation as requested (meetings, interviews, etc.) • *VITA/Agencies Security Staff – Communication to incumbent supplier of upcoming assessment and systems impacted (so that incidents are not created because access is considered a true “attack”) • VITA/Agencies Security Staff – Approvals as required • Incumbent Security Staff – Security POC for notifications, planning, etc. | 1) Review assessment methodology 2) Creation of Security Assessment Plan 3) Complete analysis of data for findings, process, procedures, etc. for current-state baseline 4) Creation of Security Assessment Report 5) Meeting with VITA - presentation of findings and review of Reports 6) Deliver Action Plan, including recommended deliverable workstreams to handle the actions 7) Delivery of all Reports and supporting data to VITA | Risk: Access/information required to complete assessment is delayed. Mitigation: Inform VITA early of the access/information required to successfully perform this assessment Risk: Activities conducted during the assessment inadvertently “trigger” incident response by current supplier Mitigation: VITA informs incumbent of upcoming assessment and the need for a Security POC to ensure incumbent is aware of ongoing assessment and potential notifications etc. that might be triggered. | -7 Months | -5 Months | -9 Months | -3 Months
5.02 | Current State Assessments | Continual Service Improvement Assessment | Operations - Process | Continual Service Improvement Assessment to discover and baseline/definition of the current processes is complete, gap analysis performed and the CSI Board is chartered, with detailed ongoing CSI Governance and implementation plans and procedures defined. | 1.03, 1.07 | • Incumbent – Availability for Knowledge Transfer sessions and provision of associated documentation including CSI register | 1) Review assessment methodology 2) Complete analysis of data for findings, process, procedures, etc. for current-state baseline 3) Assessment completed and final report with recommendations and CSI plan submitted 4) Deliver Implementation Project Action Plan, including recommended deliverable workstreams to handle the actions required to get to steady-state | Risk: Access/information to VITA and Agency personnel required to complete assessment is delayed. Mitigation: Inform VITA early of the access/information names and titles required to successfully perform this assessment Risk: Documentation of current CSI Plan, associated ongoing activities, long term roadmap etc. is not readily available, delaying the assessment Mitigation: Ensure VITA has complete list of required documentation as early as possible so they can obtain any missing items prior to assessment kickoff. | -8 Months | 0 Months | -9 Months | -6 Months
6 | Future State Assessments | IT Service Portal Design & Development Workshop | Operations - Tools | Completion of the interactive, iterative engagement that is designed to ensure the End User Portal component of Keystone Edge is delivering valuable information via a user friendly interface. | 1.03, 1.07 | • VITA/Agencies – Identification of a group of Key Stakeholders to: o Participate in a bi-weekly meeting for ongoing review of development progress o Attend 3-5 additional review meetings o Provide approval of all deliverables • VITA/Agencies – Identification of personnel to participate in one of ~ 10 discovery sessions; attendees should be from a diverse group of agencies, similar size/scope agencies can be grouped • VITA/Agencies – Identification of a larger group of VITA/Agency personnel to participate in Card Sort sessions (similar to surveys) and a “survey blast” designed to elicit relevant discovery-level information • VITA/Agencies – Identification of 20-25 participants to participate in usability testing sessions • VITA/Agencies – Evaluation of current Report requirements (Types and Frequency) and development of online alternatives/options with localized printing or email delivery o Draft Monthly Project Profile and Status report o Draft Governance Body reports and SMS dashboards o Draft BRM reports o Draft resource management and availability dashboard | 1) Meeting with Stakeholders held and minutes issued 2) Preliminary Journey Maps, design prototypes, and design recommendations delivered for review (iterate as required) 3) Finalized design and structure recommendations delivered (including Portal Value Assessment report) and approved by VITA 4) Portal optimization implementation plan and schedule developed | Risk: VITA/Agency personnel are unable to actively participate in workshop. Mitigation: Inform VITA early of the workshop schedule and required level of participation to successfully solicit feedback necessary for optimal Portal Design. Truly focus on establishing early buy-in and support for these activities. | -8 Months | -5 Months | -9 Months | -4 Months
6.01 | Future State Assessments | Innovation Forum | Operations - Management | Completion of the interactive, joint engagement that is designed to ensure the mission and business goals of VITA and the Agencies are clearly understood and that areas for targeted innovation have been identified. | 1.03, 1.07 | • VITA/Agencies- Access and dedicated availability to Commonwealth personnel • VITA/Agencies- Participate in Innovation Forum to receive feedback and input related to optimizing the MSI services’ alignment with the Customers’ missions | 1) Innovation Roadmap (including Target Innovation report) with activity descriptions, milestones and dependencies delivered and approved by VITA 2) Future State Experience Map validated by VITA and Steering Committee (Agencies) | Risk: VITA/Agency personnel are unable to actively participate in Innovation Forum Mitigation: Inform VITA early of the Forum schedule and required level of participation to successfully solicit feedback necessary for optimal collection of targeted innovations. | -8 Months | -5 Months | -5 Months | 0 Months
7 | Service Portal and Service Catalog | Service Catalog | Portal | Establishment of initial catalog of functions, services, and components for standardized request via the Service Portal or contact to the Service Desk. | 1.09, 3.00, 3.01, 3.02, 3.03, 3.04, 5.00, 6.00, 6.01, 8.02, 8.03 | • VITA – Participation in prioritization of catalog items for initial deployment based on analysis of existing STS and incumbent integration and fulfillment capabilities. • VITA – Reviews and approval of catalog item targets for initial implementation. | 1) Documentation and analysis of candidate catalog items 2) Documentation of recommended catalog items for initial deployment 3) Development of approved, initial deployment catalog items 4) Demonstration of authorized user access to request each function, service, and/or component defined by the approved initial catalog 5) Functional demonstration of full workflow (approvals, task creation/tracking/resolution, etc.) for each function, service, and/or component as defined by the approved initial fulfillment process for the catalog item 6) SMM documentation delivered for the governance and processes to affect change within the Service Catalog | Risk: Specific, desired Service Catalog items (functions, services, components) may require approval/fulfillment actions for which the responsible entity (e.g. an STS or the incumbent) has not integrated, or is not prepared to perform at commencement. Mitigation: Through preparation and review of the initial catalog contents, SAIC will identify item approval/fulfillment actions and provide recommendations for deferral, partial workflow implementation, or responsible entity remedial activities for VITA review/approval. | -6 Months | 0 Months | -6 Months | 0 Months
7.01 | Service Portal and Service Catalog | Service Portal | Portal | Establishment of the user-facing Service Portal (web-based interface to standardized functions, services, components and information) for the ITISP | 1.09, 3.00, 3.01, 3.02, 3.03, 3.04, 5.00, 6.00, 6.01 | • VITA – Reviews and approval of Service Portal design/content for initial implementation resulting from task 4.00 • VITA – Participation in prioritization of portal content for initial deployment based on analysis of existing STS and incumbent integration and fulfillment capabilities. | 1) Documentation and analysis of candidate portal components 2) Documentation of recommended portal components for initial deployment 3) Development of approved, initial deployment portal components 4) Demonstration of authorized user access to request each function, service, and/or component defined by the approved initial catalog 5) Functional demonstration of full workflow (approvals, task creation/tracking/resolution, etc.) for each function, service, and/or component as defined by the approved initial fulfillment process for the catalog item 6) SMM documentation delivered for the governance and processes to affect change within the Service Portal | Risk: Specific, desired Service Portal content may require authorization or response activities for which the responsible entity (e.g. an STS or the incumbent) has not completed integration, or is not prepared to perform at commencement. Mitigation: Through preparation and review of the initial portal contents, SAIC will identify dependencies and provide recommendations for deferral, partial implementation, and/or responsible entity remedial activities for VITA review/approval | -6 Months | 0 Months | -6 Months | 0 Months
8 | Architecture Strategy & Design | IT Service Continuity | Architecture Strategy & Design | IT Service Continuity includes the processes, procedures, and coordination of IT SCM planning and testing. | 1.09, 5.00 | • VITA/Agencies – Participation as requested (meetings, interviews, etc.) • VITA/Incumbent – Provision of existing documentation covering the current Disaster Recovery and Business Continuity Plans, Test Schedule, and Recent Test Results | 1) Service Continuity Planning Kick-off meeting conducted 2) Stakeholders interviewed 3) Existing Service Continuity Plans identified and documented 4) Updated Service Continuity Plan(s) Documented and Submitted 5) SMM procedures updated and approved by VITA | Risk: Incumbent personnel are not available for knowledge transfer sessions and/or delay the provision of documentation causing a delay in implementation activities Mitigation: 1) Provide VITA with information regarding incumbent-related participation and required data as early as possible 2) Report on disentanglement compliance and escalate issues through VITA (require participation) 3) Include slack time in schedule to allow rescheduling Knowledge Transfer 4) Hold regular progress metrics and tracking and capture adjustments during shadowing (observations of undocumented processes/tasks) 5) Regularly apprise VITA of issues and request assistance to resolve them, as needed 6) Implement the Communication Strategy elements related to the incumbent contractor 7) Resolve issues collaboratively and expeditiously 8) Minimize requirements and expectations of incumbent to provide VITA-owned data and execution of existing contract responsibilities during implementation (e.g., change management) 9) Ensure VITA gains agreement for at a minimum job shadowing to allow SAIC to document ongoing operational processes and activities | -9 Months | 0 Months | -9 Months | 0 Months
8.01 | Architecture Strategy & Design | Continual Service Improvement | Architecture Strategy & Design | Continual Service Improvement includes the collection an analysis of data to develop recommendations for improvement, maintenance of a Continual Service Improvement register, and oversight of improvement actions. | 1.09, 5.00, 5.02, 6.00 | • VITA/Agencies – Participation as requested (meetings, interviews, etc.) • VITA – Provision of existing documentation covering the current improvement plan(including identified gaps, planned/upcoming activities and details of any ongoing efforts) | 1) Initial Technology Plan updated and approved by VITA 2) CSI Assessment findings and transformation roadmap submitted and VITA approved 3) SMM procedures updated and approved by VITA | Risk: Access/information to VITA and Agency personnel required to complete assessment is delayed. Mitigation: Inform VITA early of the access/information names and titles required to successfully perform this assessment Risk: Documentation of current CSI Plan, associated ongoing activities, long term roadmap etc. is not readily available, delaying the assessment Mitigation: Ensure VITA has complete list of required documentation as early as possible so they can obtain any missing items prior to assessment kickoff. | -9 Months | 0 Months | -9 Months | 0 Months
8.02 | Architecture Strategy & Design | Service Portfolio Management | Architecture Strategy & Design | Service Portfolio Management includes the full lifecycle of service offerings including pipeline, management of standard catalog items and structure, and retirement of services. | 1.09, 5.00 | • VITA/Agencies – Participation as requested (meetings, interviews, etc.) • VITA/Incumbent – Provision of existing documentation covering the current Service Portfolio contents and Management Processes (including identified demands/gaps, planned/upcoming activities and details of any ongoing efforts) | 1) Service Portfolio Management Kick-off meeting conducted 2) Stakeholders interviewed 3) Existing Service Portfolio system(s)/processes identified and documented 4) Service Portfolio Management Plan Documented and Submitted 5) SMM procedures updated and approved by VITA | N/A | -8 Months | 0 Months | -8 Months | 0 Months
8.03 | IT Architecture & Road Mapping | IT Architecture & Road Mapping | Architecture Strategy & Design | IT Architecture and Road Mapping includes Service Strategy and IT Technology Planning. | 1.09, 5.00 | • VITA/Agencies – Participation as requested (meetings, interviews, etc.) • VITA/Incumbent – Provision of existing documentation covering the current Architecture and Road Maps | 1) IT Architecture and Road Mapping Kick-off meeting conducted 2) Stakeholders interviewed 3) Existing Artifacts and Plans identified and documented including the Initial Technology Plan 4) Updated Architecture and Road Mapping Plan(s) Documented and Submitted 5) SMM procedures updated and approved by VITA | Risk: Information from the Incumbent needed for Architecture & Road Mapping is not available or delayed Mitigation: Provide VITA with list of artifacts to be reviewed as early as possible so they can begin collection of data | -8 Months | 0 Months | -5 Months | -1 Months
8.04 | Architecture Strategy & Design | Architectural Implementation | Architecture Strategy & Design | All Architecture, Strategy, and Design functions are fully operational including: o Security Architecture Engineering o Service Continuity Management o Technology Currency o Continual Service Improvement | 1.00, 1.08, 6.01, 8.00, 8.01, 8.02, 8.03 | • Incumbent Service Desk and Service Management Staff – Availability for Knowledge Transfer sessions and provision of associated documentation including CSI register, register of current Demands and Requests for Solution, current architecture documentation, Service Pipeline data and IT continuity plans • VITA/Agencies Architects – Business Strategy, Architecture, and Security Architecture documentation to assist with full architecture view of VITA/Agency environment(s) • VITA/Agencies Service Leads – Appropriate personnel are available for CRR activities and associated sign off | ASD Staffing 1) Access to systems, equipment and locations/workspace for all staff is provided 2) Communication plan for all staff for ASD organizational effectiveness is developed/distributed 3) Staffing for all ASD tasking is available For the following ASD functions (Availability Management, Capacity Management, Improvement Planning, IT Service Continuity Management, IT Technology Planning, Process Evaluation and Currency, Service Measurement, Service Portfolio Management, Service Review and Reporting, Solution Design Management, Strategy Generation and Management, Technical Currency and Technical Innovation) 1) Key stakeholders identified (VITA, Agency, and STS personnel) 2) All activities that are being performed by the Incumbent contractor identified, along with the resources that support are known, and KT/job shadowing-where applicable-has been completed. 3) Review of the Service Management Manual and identification of any content related to each ASD activity 4) Differences between existing (i.e. SMM) processes, and our proposed processes fully documented and SMM updated 5) Service Performance Reporting (Phase I) approved by VITA 6) Agreed ongoing Communications plan with VITA, Agency, STS, and other stakeholders 7) Linkages defined for each ASD activity into the governance processes 8) ASD Commencement Readiness Reviews completed (i.e. all ASD activity processes have been tested prior to full implementation) | Risk: Incumbent personnel are not available for knowledge transfer sessions and/or delay the provision of documentation causing a delay in implementation activities Mitigation: 1) Provide VITA with information regarding incumbent-related participation and required data as early as possible 2) Report on disentanglement compliance and escalate issues through VITA (require participation) 3) Include slack time in schedule to allow rescheduling Knowledge Transfer 4) Hold regular progress metrics and tracking and capture adjustments during shadowing (observations of undocumented processes/tasks) 5) Regularly apprise VITA of issues and request assistance to resolve them, as needed 6) Implement the Communication Strategy elements related to the incumbent contractor 7) Resolve issues collaboratively and expeditiously 8) Minimize requirements and expectations of incumbent to provide VITA-owned data and execution of existing contract responsibilities during implementation (e.g., change management) 9) Ensure VITA gains agreement for at a minimum job shadowing to allow SAIC to document ongoing operational processes and activities | -9 Months | 0 Months | -9 Months | 0 Months
9 | Service Performance Reporting (Phase I) approved by VITA | Risk Management | Architecture Strategy & Design | SAIC Cyber Security Analysts performing Risk Management activities including risk assessment, mitigation, and lifecycle management in support of ITISP services. | 1.03, 1.09 | • VITA CISO - provide SAIC access to RSA Archer including access licenses for up to (8) users • Incumbent Security Staff - provide current copies of Risk Management procedures in the SMM • Incumbent Security Staff - provide copies of risk mitigation plans, action plans, and current activities underway to support risk compliance and management within the ITISP | 1) SMM Procedures for Risk Management updated and approved by VITA 2) Provide initial risk assessments for ITISP 3) Provide POAMs based on risk assessment 4) Provide Initial Security Plan 5) Process Monitoring: Security Remediation Status Reports (monthly), Emerging Threats (weekly update, monthly update, quarterly update, annual in-depth), Risk Monitoring, Identification and Assessment (weekly update, monthly update, quarterly update, annual in-depth), Risk Mitigation Activities (weekly update, monthly update, quarterly update, annual in-depth), Formal Risk Assessment (monthly update, quarterly update, annual in-depth) 6) SAIC Cyber Security Analyst access to VITA RSA Archer validated 7) SMM procedures updated and approved by VITA | Risk: Access/information to VITA and Agency personnel required to complete assessment is delayed. Mitigation: Inform VITA early of the access/information names and titles required to successfully perform this assessment | -4 Months | -2 Months | -4 Months | -1 Months
10 | Operations | Identity & Access Management | Operations - Security | MSI IAM Solution including Sailpoint and CyberARK installed, configured and integrated with Commonwealth Active Directory and able to provide IAM services for approved, integrated systems. | 1.03, 1.09 | • Incumbent - provide architecture and documentation of VITA Active Directory including domain structure, federation links • Incumbent - provide electronic integration and access between SAIC Sailpoint and VITA Active directory • Incumbent - provide documentation of user policies, role-based access criteria, user administration procedures, and compliance requirements • *Incumbent - provide network support (e.g. connectivity and firewall ports) as specified in VITA approved architecture to permit technical operation of IAM solution • VITA - approve proposed IAM architecture and design | 1) IAM connectivity to in-scope systems validated 2) IAM user account administration including create, change and delete checklist completed 3) Self-service for end user account administration checklist completed 4) Testing performed showing that relevant processes are supported by the systems 5) SMM procedures updated and approved by VITA | N/A | -8 Months | -5 Months | -8 Months | 0 Months
10.01 | Operations | Service Management Systems Implementation Complete | Operations - Tools | Service Management Systems (SMS) installed and operational, and Commonwealth specific configurations and customizations applied | 1.09, 5.00, 5.01, 7.00, 7.01, 10.00, 10.02, 10.04, 10.05 |  | 1) Identity and Access Management System installed, configured and integrated with Keystone Edge™ and CENTER™ 2) Keystone Edge™ installed and configured for base operation including supporting software modules (base package, Keystone Edge enhancements, Project Portfolio Management). Integration with IAM solution completed. 3) SAIC CENTER™ Document Data Store installed and configured. Integration with IAM solution complete. 4) Technical support staff access to IAM, Keystone Edge, and SAIC CENTER confirmed 5) Testing performed showing that relevant processes are supported by the systems 6) SMM procedures updated and approved by VITA | Risk: Required infrastructure is not available within the VITA environment for the standup of the full suite of SAIC technical tools, delaying the overall implementation of MSI services Mitigation: SAIC and VITA mutually develop and agree on an alternative system architecture and deployment plan that satisfies all requirements and meets VITA security criteria. See additional information in Exhibit 2.4, Section 4, Fallback Scenario – Potential for Alternative Infrastructure Hosting Risk: Integration and/or access to VITA systems (e.g. Active Directory) is delayed causing a delay to the implementation of the SMS suite of tools. Mitigation: Provide VITA information detailing all required integrations as early as possible to allow them to begin identifying technical personnel to assist and beginning process(es) for all required approvals. Risk: Implementation is delayed due to availability of Incumbent and STS personnel, data and electronic integration(s) Mitigation: 1) Early communications of requirements and associated timeline 2) Monitor for compliance and escalate via Governance if required 3) Engagement of the SAIC Advisory Team Risk: VITA delays or does not complete evaluation of current Reporting requirements (Types and Frequency) or online alternatives/options Mitigation: 1) Early communications of requirements and associated timeline 2) Monitor for compliance and escalate via Governance if required | -9 Months | -3 Months | -9 Months | -3 Months
10.01a | Operations | Operations Implementation | Operations - Management | Wave 1 STS Onboarding | 10.01 | • STS(s) - Engagement and execution of tasks required to integrate STS tools (e.g. monitoring, ticketing, etc.) with MSI SMS tool set as appropriate/required • VITA – Clear communication to and contractual arrangement with STS(s) requiring integration with the MSI as specified • STS(s) - Participation in required MSI provided training sessions regarding use of SMS tool set • STS(s) – Provide process documentation for their respective services for inclusion in SMM • STS(s) – Participation in Governance | 1) STS data successfully "e-Bonded" with SMS tool set as appropriate 2) STS personnel trained in use of appropriate components of SMS tool set 3) STS attending and providing input in Governance processes 4) Approval of STS(s)' SMM policies and procedures 5) STS(s) – OLAs agreed and in place | Risk: STS(s) do not integrate with SMS tool set so data is not available for use by the MSI in providing services to VITA and Agencies Mitigation: Ensure contracts with STSs have requirements for the provision of required data to MSI Risk: STS personnel do not attend required training so required data is either missing or incorrectly entered in MSI tool set requiring rework and/or operational issues Mitigation: Ensure contracts with STSs have requirements for the proper use of MSI tool set for specified functions (e.g. Change Management) | -4 Months | 0 Months | -4 Months | 0 Months
10.01b | Operations | Operations Implementation | Operations - Management | Cloud Brokerage Services available for use by the Commonwealth | 10.01 | • VITA - Provide Cloud requirements including security and architecture • VITA - Network connectivity to support cloud services established | 1) CBI infrastructure available for integration with Service Catalog, invoicing and billing |  | -3 Months | 0 Months | -3 Months | 0 Months
10.02 | Operations | Customer Relationship Survey | Relationship | Ability to collect solicited and unsolicited feedback from customers via active surveys and customer submittal via the User Portal. | 1.03, 1.09, 7.01 | • VITA/Agencies - approve of survey forms and questions | 1) Validation of access to survey capability on User Portal 2) Delivery of survey and customer satisfaction reports | N/A | -5 Months | -3 Months | -5 Months | 0 Months
10.03 | Operations | Service Management Manual Responsibility | Operations - Process | SAIC assumes operational control of the SMM | 1.09, 10.01 | • Incumbent Service Management Staff - provide full copies of the existing policy and procedure manual documents and supporting Job Aids, Instructions, and Reference documentation | 1) VITA approves revised SMM policies and procedures 2) Updated SMM documentation posted to Document Data Store 3) Access to Document Data Store for authorized users validated | Risk: Incumbent vendor is unwilling or unable to adapt services to the new SMM processes and continues to operate under legacy processes Mitigation: Monitor for compliance and take any required corrective action via Governance | -7 Months | -2 Months | -7 Months | 0 Months
10.04 | Operations | Change Management | Operations - Process | Change Management, Change Evaluation, and Release and Deployment Management services are in place. | 1.09, 10.03 | • Incumbent Service Management Staff - provide documentation of existing Change Management process including SMM components, change schedules, change requirements, pre-approved change windows, change classification and criteria | 1) SMM change management policies and procedures delivered 2) Change reports including forward schedule of change, and results of change are provided | N/A | -3 Months | -2 Months | -3 Months | 0 Months
10.05 | Configuration Management Data Base | Configuration Management Database | Operations - Tools | Configuration Management Database (CMDB) system is installed, data is populated from incumbent CMDB and Agency data sources, and base CMDB and asset management services are available for use. | 1.09 | • Incumbent Service Desk Staff – Available for Knowledge Transfer sessions and provision of associated documentation • VITA/Agencies/Incumbent/STSs Architects and Service Management staff – Provide data for CMDB CI population from existing data sources • VITA/Agencies Architects – Provide architectural documentation of systems configuration and relationships • Agency IT Managers / Agency Application Owners – Provide availability for interviews and discovery sessions to map business services to physical assets | 1) Data load of asset information completed 2) Reporting reviewed and approved by VITA, including Asset Management (monthly, subject to data limitations - e.g., incumbent data may not be refreshed during implementation period), Technical Currency (monthly, subject to data limitations - e.g., incumbent data may not be refreshed during implementation period) and General asset 3) Testing performed showing that relevant processes are supported by the systems 4) Existing CMDB data (CIs) loaded into Keystone and Business Service Mapping and asset relationships for up to 50 business services with existing system architecture and/or security architecture documentation 5) SMM procedures updated and approved by VITA | Risk: Documentation to be used for business service mapping activities is unavailable or incomplete Mitigation: VITA identifies critical business applications and begins collection of enterprise architecture and security architecture documentation for these services prior to the start of Implementation Risk: VITA stakeholders may be uncertain about our readiness for operational assumption and be uncomfortable providing our authority to proceed at the commencement for a given service area. Mitigation: 1) SAIC and VITA will discuss and agree on the readiness criteria that must be met prior to the commencement of services. 2) The SAIC Implementation Team will execute interim and final readiness review criteria prior to each service commencement. 3) SAIC and VITA will review the criteria, approach, proposed schedule, and identified timing and will adjust processes to meet VITA’s expectations. | -6 Months | -1 Month | -4 Months | 0 Months
10.06 | Operations | Operations Implementation | Operations - Management | All Operation Management areas commence. This includes the Service Desk, the Joint IT Operations Center, core ITIL life cycle functions, and information security management. All Operational Management functions are fully operational including: • Service Level Management • Service Integrations • Customer Information • Security Management • Knowledge Management • Service Desk • Service Request and Fulfillment • Incident Management • Event Management • Problem Management • Request Management • Access Management • Standard Reporting | 1.07, 1.09, 1.11, 1.12, 5.00, 5.01, 6.00, 6.01, 7.00, 7.01, 10.00, 10.01, 10.01a, 10.01b, 10.02, 10.03, 10.04, 10.05 | • Incumbent Service Desk an Service Management Staff – Availability for Knowledge Transfer sessions and provision of associated documentation • VITA/Agencies Architects – Architecture and Security Architecture documentation for major business applications to assist with relationship mapping in CMDB • VITA/Agencies Service Leads – Appropriate personnel are available for CRR activities and associated sign off | 1) Service Portal configured and testing completed 2) Service Management Systems fully configured, populated, tested and approved for operations. 3) Request and Incident Management queues configured and tested including priorities, base SLA and OLA thresholds and alerts, and routing with solver groups 4) Services Implementation Readiness Plan developed, reviewed and will be approved by VITA 5) Incident Management training completed 6) Problem Management team training completed 7) Change Management schedules established and loaded into Keystone Edge 8) Change Management training completed 9) “Accessing Services” training materials completed and available 10) Commencement Readiness reviews completed 11) VITA and Agency stakeholders approve Operational Readiness checklist | Risk: Incumbent personnel are not available for knowledge transfer sessions and/or delay the provision of documentation causing a delay in implementation activities Mitigation: 1) Provide VITA with information regarding incumbent-related participation and required data as early as possible 2) Report on disentanglement compliance and escalate issues through VITA (require participation) 3) Include slack time in schedule to allow rescheduling Knowledge Transfer 4) Hold regular progress metrics and tracking and capture adjustments during shadowing (observations of undocumented processes/tasks) 5) Regularly apprise VITA of issues and request assistance to resolve them, as needed 6) Implement the Communication Strategy elements related to the incumbent contractor 7) Resolve issues collaboratively and expeditiously 8) Minimize requirements and expectations of incumbent to provide VITA-owned data and execution of existing contract responsibilities during implementation (e.g., change management) 9) Ensure VITA gains agreement for at a minimum job shadowing to allow SAIC to document ongoing operational processes and activities 10) SMM procedures updated and approved by VITA Risk: Delays in or unwillingness to provide data from current CMDB data sources impact the schedule for population of MSI tool set Mitigation: Ensure all potential data sources are identified as quickly as possible so VITA can ensure that they, at a minimum, are able to obtain that data in a suitable electronic format from all potential sources | -7 Months | 0 Months | -7 Months | 0 Months
10.07 | Operations | MSI Service Commencement | Operations - Management | All services of the MSI are in place and operational. | 3.07, 4.01, 8.04, 10.06 | • VITA approves Go-Live | 1) Personnel hired and trained 2) Tools stood up, configured, loaded and pass UAT 3) Process documentation completed (including SMM) and in process control 4) Training completed (SAIC, VITA, Agency and STSs) 5) All services pass VITA/ITISP/Agency Commencement Readiness Review (CRR). | Risk: SAIC’s solution does not fully address the current “pain points” of VITA and the agencies, which impact the adoption of and participation in the new services; customer satisfaction is consequently not improved. Mitigation: 1) Conduct an Innovation Forum and User Experience and Design Process workshop early in the implementation with VITA and agency personnel to ensure that the SAIC solution addresses and is designed to improve services in the areas that are important to the consumers of our solution 2) Provide a mechanism for feedback during the implementation of services (e.g., have beta versions of the service portal and other technologies available for testing and associated feedback) 3) Charge the SAIC Implementation Team with executing interim and final readiness review prior to each service commencement. | -9 Months | 0 Months | -9 Months | 0 Months
11 | Business Relationship Management | Business Relationship Management Readiness | Relationship | SAIC BRM Management team in place to hire requested number of Business Relationship Management to provides direct support to Vita's CAM's by assume responsibility for day-to-day operational activities allowing the CAM's to focus on agencies strategic direction, budget, and business case development. | 1.03, 1.04, 1.09, 7.01 | • VITA/Agencies/Incumbent/STS’s – Informed of SAIC’s BRM’s roles • VITA/Agencies - Access and dedicated availability to Commonwealth personnel • VITA/Agencies/Incumbent - Availability for knowledge transfer and discovery sessions • VITA/Agencies – Establishment of communication and action plans • VITA/STSs – Access and availability to STS’s personnel and contracts | 1) Meeting minutes with VITA, agencies, incumbent and STS’s taken and distributed 2) Mapping of agencies responsibilities, activities, report requirements, projects, priority objectives and critical milestone timelines 3) Document processes and procedures developed for BRM. 4) SMS tools are tested to indicate support of these processes. 5) Sign-off on communication and action plans 6) SMM procedures updated and approved by VITA | Risk: Limited services and reporting available to Agencies Mitigation: Clear communication by VITA to Agencies shareholders Risk: Access and commitment of Commonwealth Agency personnel for training and workshops Mitigation: Early communications by VITA to Agencies shareholders of personnel training plans, training dates and workshop dates. | -9 Months | 0 Months | -9 Months | 0 Months