## Title Page
VA-170822-SAIC Mod 14 | Exhibit 2.4.2 Optional Services Milestones
Exhibit 2.4.2 Optional Services Milestones VA-170822-SAIC - MOD. 14
COMMONWEALTH OF VIRGINIA VIRGINIA IT AGENCY (VITA) SUPPLIER STRATEGY AND PERFORMANCE 11751 MEADOWVILLE LANE CHESTER, VIRGINIA 23836

## eVA Integration
Ref # | Milestone | Milestone Name | Milestone Description | Acceptance Criteria | Due Date
1 | EVA-01 | Requirements Session | Field identification, requirements doc, security levels, workflows | Requirement documents completed and approved by VITA and Agency stakeholders | TBD
2 | EVA-02 | Build new bifurcated Workflow for Catalog items | Development of a workflow that provides 2 paths (1 for items with cost and 1 without cost) | 1) Test script that shows creation of a) RITM for non-costed items in KSE and b) On the order of an item will show appropriate user message, directions, and link to eVA for order creation of costed items completed and approved by VITA and Agency stakeholders 2) UAT Test Plan and Cases completed and approved by VITA and Agency stakeholders | TBD
3 | EVA-03 | UAT Retest/Completion | Document output and outcomes of UAT test and sign-off- Document | UAT Test Plan and Cases completed and approved by VITA and Agency stakeholders | TBD
4 | EVA-04 | Release to Production | Final Acceptance and Payment | All functionality is working as documented in requirements and during UAT testing as confirmed by VITA and Agency | TBD
*Note- VITA and MSI agree that milestone due dates will be agreed upon and formally documented in a contract notice.