## Title Page
VA-1801012-ATOS, Mod-23 | Exhibit 2.4.1 Implementation Milestones
Exhibit 2.4.1 - MOD 23 Implementation Milestones VA-180112-ATOS
COMMONWEALTH OF VIRGINIA VIRGINIA INFORMATION TECHNOLOGIES AGENCY (VITA) SUPPLY CHAIN MANAGEMENT DIVISION 7325 Beaufont Springs Drive Richmond, VA 23225

## Overview
Overview
This Milestones Exhibit will allow VITA to better understand the key phases, events, and timing of the Supplier's plans.
The worksheet reflects the major events of Supplier's contract lifecycle, including the Implementation Plan for implementing the Services and ongoing programs for maintaining and updating the Services, with verifiable criteria for acceptance. Milestones reflect the key events indicated over the course of the Implementation Plan and the overall term of Supplier's agreement. The Milestones will align with other documents as appropriate.
The worksheet is not intended to be a detailed project plan, but rather a list of key milestone activities. The Supplier may add to or delete rows from the worksheet as necessary.
Definitions of Fields
Ref ID # | Unique identifier, to be used at Supplier's option, to tie to other documents (e.g., Implementation Plan, Solution, Critical Deliverables, etc.)
Milestone | Name of the milestone
Category | Name of a grouping of activities (e.g., Service Desk, security) - to be determined at Supplier's option.
Description | Description of the activities comprising the milestone
Dependencies on Other Milestones (Ref #) | Indicate the reference numbers of predecessor/dependent milestones to support the current milestone.
Dependencies (i.e., on Commonwealth or Incumbents) | Describe dependencies or expectations of the incumbent suppliers, VITA, agencies, etc.
Risk Mitigation Approach | Describe the risk mitgation approach for any issues with the dependencies indicated in the prior columns.
Acceptance Criteria | Description of Acceptance Criteria, which will indicate completion of the milestone.
Start Date (Comm +/- Months) | Date when the activity begins in support of the milestone, in Months relative to Commencement.
Due Date (Comm +/- Months) | Date when the milestone will be completed in Months relative to Commencement (i.e. +/- number of months). Fractional values of 0, .25, .5, or .75 may be used.

## Implementation Milestones
Milestones
Ref # | Milestone | Category | Description | Dependencies on Other Milestones (Ref #) | Dependencies (i.e., on Commonwealth or Incumbents) | Risk Mitigation Approach | Acceptance Criteria | Start Date | Due Date
CMT-0 | Pre-Transition Planning | Project Mgt. & Security | Development of High Level Design, Process Planning and Documentation - preparation actives for transition and transformation phases. Overall objective to ensure the most efficient transition and transformation planning. preparation of training material. Initial contact and interview of dedicated staff. (HR onboard process), Procurement of hardware and software assets. | Contract Signature | VITA / MSI Documentation Templates | N/A | N/A | Contract Signature | 5.0 Months before Kick off Date
CMT-1 | Transition Kick-Off Workshop Completed | Project Mgt. | Purpose of the Joint Transition Workshop is to review VITA RFP requirements; clarify any open issues or concerns; document and agree on milestone dates, start and finish dates, dependencies and resources needed for each task and generally ensure that both parties are aligned as to scope, timing, tasks, responsibilities, etc. Additionally, Atos will utilize the MSI monthly governance structure to provide program updates and will utilize the MSI for escalations and this will be included as part of the Joint Workshop. | N/A | Contract Signature and Active Participation in Workshop | N/A | Updated implementation plan and timeline, and Workshop completed. | Kick Off Date | 0.5 Months from Kick off Date
CMT-2 | Detailed Transition Schedule (DTS) | Project Mgt. | Purpose of the Transition Schedule is to ensure that both parties are in complete agreement on start and finish dates, dependencies and resources needed for each task. Once the Schedule is baselined, all changes must follow the formal Change Request process. | CTM -1 | Participation in Workshop and collaboration in finalizing Project Schedule | Strong collaboration and communications | Draft Project Plan delivered. Draft Transition Change management process document delivered. Draft communication process delivered. | 0.25 Months from Kick off Date | 2 Months from Kick off Date
CMT-3 | Knowledge Transfer Plan, Revised Project Plan Draft, Key Personnel | Move trans schedule | This is the plan that identifies all the knowledge objects required to take-over operations and identifies the different strategies and mechanisms to obtain that knowledge (e.g., documentation, interviews, presentations, shadowing) - Draft version of billing triggers document (enhanced version of Exhibit 4.9), revised project plan. | CMT-1 |  |  | Atos provides a detailed plan with all the knowledge objects required, the approach to perform the knowledge transfer, the participants, the time line to accomplish it, the dependencies on other parties and the evidence to be provided to consider the knowledge transfer process completed. Finalized key personnel document. - Draft version of billing triggers document (enhanced version of Exhibit 4.9), and project plan. | 0.25 Months from Kick off Date | 2.5 Months from Kick off Date
CMT-4 | SMM and Training Plan Initial Drafts Submitted. Final Communication Process and Transition Change plan. |  | SMM Initial Draft submitted. Transition Change management process document delivered. Established communication process provided. This includes the Draft Customer Training Plan. | CMT-2 | VITA's review and recommended edits to the Draft Transition Change management process document delivered. Established draft communication process provided. Baseline project plan. | Drafts will be finalized as it. | Transition Change management process document delivered. Established communication process provided. This includes the Draft Customer Training Plan. SMM Draft. | 0.25 Months from Kick off Date | 3.5 Months from Kick off Date
CMT-5 | Knowledge Transfer Complete, SMM Final Due | Project Mgt. | Knowledge has been transferred and that the provider is ready to take over the in-scope operational environment. SMM final is for the WITO services only. WITO Services are as follows: SIEM/SOC solution is operational Digital Forensics End Point Security solution is operational Vulnerability Assessment and Compliance solution is operational Certificate Management platform is operational Web/Perimeter Firewalls Perimeter / Managed IDS/IPS Web Proxy Full Packet Capture | CTM-3 | Active participation from Incumbent, MSI and VITA | Project plan and milestones are re-baselined | The evidence knowledge transfer has been successfully completed and the commitment that Atos is ready to take over the operational environment. SMM Final delivered | 3.5 Months from Kick off Date | 6.5 Months from Kick off Date
CMT-6 | MSI Integration. Final Billing Triggers Due | Security | Integration with MSI ITSM systems which are available at the time deliverable is due. | CTM-3 | MSI ITSM Tool sets are available | Project plan and milestones are re-baselined and delay integration until services are ready | Finalized version of billing triggers document (enhanced version of Exhibit 4.9) Applicable integration with MSI is complete and demonstrated to VITA. Minimum MSI Integrations are Incident, Change, Configuration/CMDB, ITFM, and Request/Service Catalog. | 6 Months from Kick off Date | 7 Months from Kick off Date
CMT-7 | Security Go-Live | Security | This milestone requires the completion of the following tasks for the interim mode of operations: a) Atos has full control, adequate staffing, documented processes/procedures in place to support the security services identified and agreed upon. b) Atos Security Operations Center services using existing tools and technology is documented, operational, tested and validated. | All earlier CMT's | Active participation from Incumbent, MSI and VITA. Agreement on services atos is taking over as part of commencement on 12/3. | Delay Go-Live if required, Project plan and milestones are re-baselined. | Security services Go-Live for the interim mode of operation systems identified in CMT-5: Atos has full control, documented processes and procedures of the existing security service provided by the incumbent. Atos Security Operations Center services using existing tools and technology is documented, operational, tested and validated | 1.0 Months from Kick off Date | 7 Months from Kick off Date
CMT-8 | Validate backup, restore and system monitoring for WITO |  | Validate backup and restore for WITO systems are functional and validate system monitoring for WITO systems are functional | CMT-7 | Current Data Center STS (Vendor) provide sufficient backup space and technology. Current Data Center STS (Vendor) provide sufficient system monitoring technology and is configured to monitor designated systems in the Atos solution | Backups and system monitoring will not be provided | Validate backup and restore for WITO systems are functional and Validate system monitoring for WITO systems are functional | 7 Months from Kick off Date | 7.25 Months from Kick off Date
CMT-9 | Transition Complete and Closed | Project Mgt. | Atos activities to close the Transition Project, including Atos Internal review and approval, Handoff to Operations (delivery) is thoroughly reviewed and approved, and VITA has verified acceptance testing results, reviewed and approved all required transition activities. | CMT-7 | VITA approval and sign-off of the Commencement Readiness Review. | Conduct advance planning, and review and approval of Transition Closure criteria before proceeding. | Atos demonstration that tools and associated processes identified in CMT-5 are working as intended. | 2018-12-03 | 7 Months from Kick off Date
CMT-10 | HyperCare Completed | Security | This Milestone promotes increased level of visibility of End User issues during Go-Live and ensures a strong focus and availability of resources required to address issues as quickly as possible. | All earlier CMT's | VITA approval and sign-off | Active participation from all parties |  | 2018-12-03 | Commencement + 1 Month
CMT-11 | Modernized Security Services Installed. | Security | This milestone requires the completion of the following tasks: These New Security Services are installed: *Atos SIEM solution *Atos End Point Security is solution Endpoint security includes: Malware protection, Host based Firewall, Host based IPS, DLP, Application Whitelisting, Threat Intelligence, Dynamic Application Control, Active Response, File Integrity, File and folder encryption and Hard drive encryption *Network DLP *Atos Vulnerability Scanning and Compliance *Atos Application Vulnerability Scanning (Application Scanning suspended on the MOD 23 Effective Date) *Source Code Scanning *CASB Security Services *NAC Security Services *Tokenizarion Security Services *Certificate Management Security Services | CMT-3 | VITA has provided sufficient access to Atos Staff to install equipment in VITA primary data center. This includes network access, power and cooling. | Project plan and milestones are re-baselined | Infrastructure ready for pilot testing. Tools are installed, configured, and integrated (if needed, within the Atos enclave). | 1.0 Months from Kick off Date | Commencement + 2.5 Months
CMT-12 | Modernized Security Services Pilot | Security | Modernized Atos Services below will be tested in a pilot environment: SIEM agent/or configuration of pilot log data sources to SIEM ePO agent to pilot servers or workstations Vulnerability and Compliance Scanning End Point for Servers and Workstations Application Process Whitelisting Hard Drive & File Level Encryption TIE and DLP integration NAC Tokenization Certificate Management CASB Source Code Scaning | CMT-11 | CASB scope is defined by VITA |  | 1. Acceptance testing plans approved by VITA. 2 Pilot encompasses testing of functionality of systems and any installed test systems to validate system operational status. 3. Demonstrated integration with MSI Toolset. | 6.0 Months from Kick off Date | Commencement + 3.5 Months
CMT-13 | Customer Training Complete | Security | Atos completes the execution of the approved Customer Training Plan (included in CMT-5) and conduct Customer-focused training with regard to operational aspects of the toolset. | CMT-11 | Customer Training Plan has been approved. Security services platform is operational. Applicable MSI integration is complete. Reporting elements have been approved and completed | Conduct advance planning, and review and approval criteria before proceeding. Communicate any risk or delays to MSI and VITA | Atos to provide evidence of the delivery of Customer-focused training as per Customer Training Plan with regard to operational aspects of the toolset (i.e., presentation materials, schedules) Training Documentation | 6 Months from Kick off Date | Commencement + 4 Months
CMT-14 | Modernized Security Services Go-Live | Security | This milestone requires the completion of the following tasks: New Security Services are operational. They are documented, fully operational, tested, validated and ready to accept Commonwealth Assets for service: *Atos SIEM solution *Atos End Point Security solution Endpoint security includes: Malware protection, Host based Firewall, Host based IPS, DLP, Application Whitelisting, Threat Intelligence, Dynamic Application Control, Active Response, File Integrity, File and folder encryption and Hard drive encryption) *Network DLP *Atos Vulnerability Scanning and Compliance *Atos Application Vulnerability Scanning (Application Scanning suspended on the MOD 23 Effective Date) *Source Code Scanning Service *CASB Service *NAC Service *Tokenization Service *Certificate Management | CTM-11 | Active participation. | Delay Go-Live if required, Project plan and milestones are re-baselined | New Security Services below are operational. They are documented, fully operational, tested, validated and ready to accept Commonwealth Assets for service: *Atos SIEM solution *Atos End Point Security solution Endpoint security includes: Malware protection, Host based Firewall, Host based IPS, DLP, Application Whitelisting, Threat Intelligence, Dynamic Application Control, Active Response, File Integrity, File and folder encryption and Hard drive encryption) *Network DLP *Atos Vulnerability Scanning and Compliance *Atos Application Vulnerability Scanning (suspended on the MOD 23 Effective Date) *Source Code Scanning Service *CASB Service *NAC Service *Tokenization Service *Certificate Management | 2018-12-03 | Commencement + 4 Months
CMT-15 | Validate backup, restore and system monitoring for Modernized Services - |  | validate backup and restore for MODERNIZED systems are functional and validate system monitoring for WITO systems are functional | CMT-14 | Current Data Center STS (Vendor) provide sufficient backup space and technology. Current Data Center STS (Vendor) provide sufficient system monitoring technology and is configured to monitor designated systems in the Atos solution | Backups and system monitoring will not be provided | validate backup and restore for MODERNIZED systems are functional and validate system monitoring for MODERNIZED systems are functional | 7 Months from Kick off Date | Commencement + 5.5 Months
CMT-16 | Clean up activities | Security | This milestone is to clean up any agency migration which were not completed due to unforseen change windows. | CMT11 - CMT-14 | Active Participation in Workshop | Ensure clearly documented change windows by agency |  | Commencement Date | Commencement + 6 Months