## Title Page
VA-20180815-UC - MOD. 6 | Exhibit 2.4.1 Implementation Milestones
Exhibit 2.4.1 - MOD. 6 Implementation Milestones VA-20180815-UC
COMMONWEALTH OF VIRGINIA VIRGINIA INFORMATION TECHNOLOGIES AGENCY (VITA) SUPPLY CHAIN MANAGEMENT DIVISION 11751 MEADOWVILLE LANE CHESTER, VIRGINIA 23836

## Implementation Milestones
Milestones
Ref # | Milestone | Category | Milestone Name | Milestone Description | Dependencies on Other Milestones (Ref #) | Acceptance Criteria | Start Date (Comm +/- Months) | Due Date (Comm +/- Months)
1 | M-01 | Plan | Effective Date | Project starts. | Not applicable | Not applicable | Effective Date | Effective Date
2 | M-02 | Plan | Kickoff Meeting Held | Initial Kickoff meeting | M-01 | Kickoff meeting minutes reviewed and accepted. |  | Effective Date +1 Week
3 | M-03 | Plan | Governance Established | Governance structures and cadence developed and instituted. | M-01, M-02 | - Governance org charts published - Initial governance meetings scheduled - Reporting templates and details provided - Governance roles confirmed and dedicated to project | Effective | Effective Date +2 Weeks
4 | M-04 | Plan | Services Detailed Implementation Plan (CD 3.1) | Detailed project schedule approved. One EXHIBIT 3.3 Critical Deliverable. | M-01, M-02, M-03 | Services Detailed Implementation Plan includes: - Knowledge Transition - HR Staffing Plan - MSI Process Integration - SMS Implementation - Published project schedule in Microsoft Project format | Effective | 2018-09-19
5 | M-05 | Cross-Functional | SMM Initial Draft Complete (CD 3.3.1) | Initial STS content for the SMM developed EXHIBIT 3.3 Critical Deliverable. | M-01 | Initial SMM content delivered. | Effective | 2018-10-15
6 | M-06 | Cross-Functional | Work In Progress Readiness Completed | In-flight projects have been reviewed and documented with plan and process to manage at commencement. | M-01, M-02, M-03 | - List of current Work In Progress - Readiness, including resources, for Supplier assumption of in-flight project work on Service Commencement - Process to monitor and manage list between milestone and Comm - Readiness to participate in MSI governance forums and PMO | Effective | Comm - 2 Months
7 | M-07 | Infrastructure and Tools | Technology Infrastructure Readiness for Commencement | New infrastructure, tools, and connectivity is deployed to support MSI process integration, SMS Implementation, and Reporting for Commencement. Includes: - Event Management - VPN / Networking Connectivity (including Eagan and Salt Lake City) - Discovery Scanning Tools - CESC and Secondary Data Center | M-01, M-02, M-03 | - Unisys tools are in place, configured, and Unisys is prepared to deliver in-scope services using Unisys tools. | Effective | 2019-04-23
8 | M-08 | Knowledge | Knowledge Transfer Completed | Knowlege Transfer has been completed and documented | M-01, M-02, M-03 | - Existing, legacy Technical Documentation provided - Knowledge Transfer interviews completed - Gap Assessment report provided | Effective | Comm - 1 Month
9 | M-09 | Cross-Functional | SMM Final Document (CD 3.3.2) | STS content for the SMM is finalized and approved EXHIBIT 3.3 Critical Deliverable. | M-01, M-02, M-03 | SMM content delivered for review and approval by MSI and VITA. | Effective | 2019-03-01
10 | M-10 | Readiness | Initial Security Plan Completed (CD 3.5) | Supplier Security Plan has been reviewed, approved, and submitted for integration into the overall security model EXHIBIT 3.3 Critical Deliverable. | M-01, M-02, M-03 | Security Plan delivered. Security plan collaboration and status provided weekly starting 1/5/19. | Effective | 2019-02-15
11 | M-11 | Readiness | Staffing Readiness Completed | Sufficient Supplier staff are in place, trained, and have appropriate access for assumption of services. MSI training on tools and processes completed | M-01, M-02, M-03 | - Staffing model completed - Relevant accounts created and credentials provided (ie user / administrative / root-level) for all in-scope environments - Physical access to work environments - MSI tools and processes training completed | Effective | Comm - 0.5 Month
12 | M-12 | Readiness | Service Catalog and Fulfillment Process Completed (CD 3.8) | Supplier catalog items have been created and submitted for inclusion into the program catalog. Fulfillment processes have been defined and actionable on Comm. EXHIBIT 3.3 Critical Deliverable. | M-01, M-02, M-03 | Catalog items submitted for inclusion to the program Service Catalog. Fulfullment of Service Catalog services ready and actionable on Commencement. | Effective | 2019-05-07
13 | M-13a | Cross-Functional | Assumption of current legacy tools and reporting | Assumption of current legacy tools and reporting | M-01, M-02, M-03 | - Assumption of current legacy tools for alerts, monitoring, reporting, and management of the environment. | Effective | 2018-12-15
13 | M-13b | Cross-Functional | SMS Implementation (CD 3.9) and Service Performance & Reporting (CD 3.4) Completed | SMS tool integration and Service Performance & Reporting implemented EXHIBIT 3.3 Critical Deliverables | M-01, M-02, M-03 | - SMS integraton and reporting are complete * ITFM will consist of CSV/XLS file * Event, Capacity, and IT Infrastructure Moniotring are live, but not SMS integrated * Service Level Management will be live, with agreed upon reports | Effective | 2019-04-23
14 | M-14 | Readiness | Initial Asset Inventory and CMDB Data Population | Discovery and physical inventory is updated into the CMDB for in-scope infrastructure, middleware, and databases. This does not include application and business mapping conducted by the MSI. | M-01, M-02, M-03 | - Tools operational - Initial scan and population of CMDB in-progress | Effective | 2019-04-01
15 | M-15 | Readiness | Assets Transfer Readiness Complete | Known incumbent assets prepared for transfer or available for Supplier use. Process for ongoing identification and resolution of additionally discovered assets in place. | M-14 | - Assets either transferred or access and use provided - Process and governance established for resolving any additionally discovered assets | Effective | 2019-12-15
16 | M-16a | Readiness | Services Implementation Readiness Plan Complete (CD 3.2) | The plan to demonstrate readiness for 12/15/18 assumption of existing operations is completed and approved | M-01 through M-15 | Service Implementaion Readiness Plan: - Staffing Readiness Completed - Knowledge Transfer Completed - Work In Progress transition-ready - Readiness to participate in MSI governance forums and PMO - Operational Readiness Review (ORR) | Effective | 2018-12-15
16 | M-16b | Full Service Readiness | Updated Services Implementation Readiness Plan Complete (CD 3.2) | The updated plan to demonstrate readiness for Full Service Delivery EXHIBIT 3.3 Critical Deliverable. | M-01 through M-15 | M07, M13B, and Operational Readiness Review complete; Updated Service Implementation Readiness Plan approved by VITA. | Effective | 2019-04-30
17 | M-17 | Readiness | Go/No-Go Decision | Governance approves Comm go-live. | M16 | Governance concurrence of Supplier readiness to go-live. | Comm - 0.5 Months | Comm - 0.5 Months
18a | M-18 | Go-Live | Commencement | Supplier assumes service from incumbent | M-17 | -Services have been assumed as-is, with Unisys acting as resolvers in MSI ServiceNow, and using existing tools and MSI-defined and implemented processes -Completion of all Implementation Milestones by 5/07/2019 | Comm + 0 Months | 2018-12-15
18b | M-18 | Go-Live | Full Service Delivery | Supplier implements complete tool set and operational capabilities | M-17 | • Services have been assumed per agreement. • All Unisys monitoring tools are deployed and functional • ITFM tools integration • Event Management integrated with SMS • Capacity Management integrated with SMS • IT Infrastructure monitoring integrated with SMS • SLA reports complete | Comm + 0 Months | 2019-05-07
18c | M-18 | Go-Live | Asset Integration Complete | This milestone confirms complete integration of all software and hardware components into the CMS/CMDB via an electronic interfacing process as outlined in the Contract Implementation Plan. | M-17 | For three agencies (to be provided to STS and SAIC by VITA upon STS submission of completion of the CMS/CMDB hardware and separately software integrations) Supplier and SAIC to provide all mapped data (hardware and separately software) to VITA in either .csv, .dat, .txt or .xlsx format and include file headers. The data must be provided within 24 hours of receiving the names of the three agencies. A comparison of the data must result in STS meeting the 95% expected SLA threshold. | 2020-12-31 | 2020-12-31
19 | M-19 | Go-Live | Hypercare Complete | Hypercare period after Comm is concluded. | M-18 | - Hypercare period is completed and significant issues related to commencement are resolved. | Comm + 0 | Comm + 1 Month
20 | M-20 | Post Implementation | Complete Asset Inventory and CMDB Data Population (CD 3.7) | Discovery and physical inventory is updated into the CMDB for in-scope infrastructure, middleware, and databases. This does not include application and business mapping conducted by the MSI. EXHIBIT 3.3 Critical Deliverable. | M-14 | - DC (primary and secondary) Physical Inventory Completed - Discovery Scanning Completed - Does not include applications (except for those that are discoverable) - CMDB Discovery "delta" files provided to MSI for CMDB update by MSI | Comm -1 Month | 2019-04-30
21 | M-21 | Post Implementation | Enhanced Automation and Reports Completed | Completion of remaining SMS integration and reports | #19b, #19c | - ITFM tools integration - retire data file feed method - Event Management integrated with SMS - Capacity Management integrated with SMS - IT Infrastructure Monitoring integrated with SMS - SLA remaining reports completed | Effective | 2019-04-23
22 | M-22 | Service Innovations | CMP Deployed | Cloud Management Platform is deployed in Supplier data center. | M-01, M-02, M-03 | Demonstration that CMP is deployed and operational per design. | Effective | 5/07/2019
23 | M-23 | Service Innovations | Initial Technology Plan (CD 3.6) | The Initial Technology Plan. Includes all data centers (CESC, Secondary, and Agencies) EXHIBIT 3.3 Critical Deliverable | M-20 | Inital draft of the Technology Plan (ITP) delivered to MSI, includes: -All existing and projected hardware and software are depicted via a roadmap -Scheduled refresh and software currency activities -Projections and schedules of technology implementations | Comm -1 Month | 2019-04-15
24 | M-24 | Service Innovations | Prioritized Remediation (based on the Initial Technology Plan) Completed | Prioritized remediation (based on Initial Technology Plan) completed. Remediations are focused on: - preparation for primary data center migration - Infrastructure currency - supportability | M-23 | Remediations are completed or alternative methods approved to enable the first migration. | Comm + 2 Months | 2019-05-17
25 | M-25 | Closing | Implementation Project Close | All closing processes have been completed for the project and VITA signoff on the Implementation Project has been received. | M-01 through M-24 | Project closure documentation delivered, indicating that all necessary implementation activities have been completed. | Comm - 5 Months | 2019-06-26