## Title Page
VA-20180815-UC - MOD. 6 | Exhibit 2.4.2 Primary Data Center Migration Milestones
Exhibit 2.4.2 Primary Data Center Migration Milestones VA-20180815-UC - MOD. 6
COMMONWEALTH OF VIRGINIA VIRGINIA INFORMATION TECHNOLOGIES AGENCY (VITA) SUPPLY CHAIN MANAGEMENT DIVISION 11751 MEADOWVILLE LANE CHESTER, VIRGINIA 23836

## Primary DC Migration
Ref # | Milestone | Category | Milestone Name | Milestone Description | Dependencies on Other Milestones (Ref #) | Dependencies (i.e., on Commonwealth or Incumbents) | Risk Mitigation Approach | Acceptance Criteria | Start Date | Due Date
1 | PDC-01 | Plan | Kickoff Meeting Held | Initial meeting. | Exh 2.4.1 M-23, M-24 in-progress | VITA and MSI key staff available to meet within 1 week of Effective Date. VITA provides space to host kickoff meeting VITA and MSI review and approve kidkoff agenda MSI will provide appropriate coordination with all STS providers. | Accept. The Kickoff is a dependency on all follow-on planning activities. Supplier is available to meet prior to Effective Date. | Kickoff meeting minutes reviewed and accepted, either tacitly or formally. (lack of input on the minutes constitutes tacit approval) | 2019-03-29 | 2019-03-29
2 | PDC-02 | Plan | Migration Governance Established | Governance structures and cadence developed and instituted for purposes of migration assessment and migration | PDC-01 | VITA and MSI staff are assigned to governance roles, and MSI governance cadence, reporting, and relevent templates are approved and in place. Assigned VITA and MSI staff attend all governance, project, change, and service review meetings. VITA provides comments and input around mangement and proposed mitigations of project risks. VITA will resolve identified project issues in a timely fashion to allow completion of the Implementation timeline | Defer formal governance activities and MSI-defined workaround for Supplier to produce ad hoc reporting until formal governance is established. | Governance org charts published, initial governance meetings scheduled. Reporting templates reviewed and approved. | 2019-03-15 | 2019-04-12
3 | PDC-03 | Plan | Initial Assessment | Assessment of starting conditions and initial risks associated with CESC migration | PDC-02 | VITA assigns appropriate personnel to answer questions about each application to understand dependencies, groups of related applications, to determine best migration approach. VITA provides Application documentation showing logical and physical architecture. VITA coordinates these activities with the respective Agencies. | Accept. Unisys will assess based on best available information, including discovery scans and migration tool reports and provide initial assessment and recommendations to VITA | Assessment report issued. |  | 2019-03-15
4 | PDC-04 | Plan | CESC Migration Strategy and Baseline Migration Plan | - Develop stategy for migrating CESC workload - Create model to be used by Agencies to estimate the number of hours per resource type - Define agency resource roles - Hours needed by resource role - (take into consideration the complexity of application and services for migration) - Baseline Migration Plan (detailed project schedule) | PDC-03 | VITA and MSI: - assigns appropriate personnel and SME's regarding each application, to understand dependencies, groups of related applications, to determine best migration approach - provide input into development of the detailed schedule - reviews and approvals - provide resources appropriate to the completion of planned tasks | Escalate within governance structures. Completion of the strategy and migration plan is critical to the timely migration of the CESC workload. | - Strategy for migrating CESC workload - Model for Agencies for resource estimation - Baseline Migration plan with groups - Published in MS Project format - Approval by VITA and MSI | 2019-04-15 | 5/17/2019
5 | PDC-05 | Infrastructure | Base Migration Infrastructure Deployed | New infrastructure is deployed. | PDC-04 and 2 weeks after STS (ATOS) fully deploys the Firewall | VITA arranges for Agency support staff to assist in platform design and selection |  | All base infrastructure buildout and configuration is complete. |  | 6/30/2020
6 | PDC-06 | Commencement | Migration Commencement Date | Currently projected as Jan 2020 | PDC-04, 05 | VITA approves the migration project | Accept. Governance decision to provide decision re the CESC data center | Governance meeting minutes |  | 8/14/2020
7 | PDC-07 | Migration | 15% Workload Migrated | 15% of CESC-based workload migrated to Supplier's new primary data center - Priority should be CESC Infrastructure and VITA servers and assets | PDC-04, 05, 06 | VITA negotiates migration date and scope with Agency and approves the final migration timeline and run book. VITA and Agencies provide resources to participate in migration activities, including governance, planning, application analysis, review and approval of deliverables, migration simulations, and other activities as needed. VITA and Agencies create the user acceptance plan and execute acceptance plan after workload migration. | Accept. Migrations cannot be completed without VITA and/or Agency dependencies. Timeline will extend until provided | Testing confirms that all planned migrations have been completed successfully. Legacy environment decommissioned as applicable. CMDB, reporting, and billing records updated. |  | 11/14/2020
8 | PDC-08 | Migration | 30% Workload Migrated | 30% of CESC-based workload migrated to Supplier's new primary data center | PDC-07 | VITA negotiates migration date and scope with Agency and approves the final migration timeline and run book. VITA and Agencies provide resources to participate in migration activities, including governance, planning, application analysis, review and approval of deliverables, migration simulations, and other activities as needed. VITA and Agencies create the user acceptance plan and execute acceptance plan after workload migration. | Accept. Migrations cannot be completed without VITA and/or Agency dependencies. Timeline will extend until provided | Testing confirms that all planned migrations have been completed successfully. Legacy environment decommissioned as applicable. CMDB, reporting, and billing records updated. |  | 2020-11-14
9 | PDC-09 | Migration | 50% Workload Migrated | 50% of CESC-based workload migrated to Supplier's new primary data center | PDC-08 | VITA negotiates migration date and scope with Agency and approves the final migration timeline and run book. VITA and Agencies provide resources to participate in migration activities, including governance, planning, application analysis, review and approval of deliverables, migration simulations, and other activities as needed. VITA and Agencies create the user acceptance plan and execute acceptance plan after workload migration. | Accept. Migrations cannot be completed without VITA and/or Agency dependencies. Timeline will extend until provided | Testing confirms that all planned migrations have been completed successfully. Legacy environment decommissioned as applicable. CMDB, reporting, and billing records updated. |  | 2021-02-14
10 | PDC-10 | Migration | 70% Workload Migrated | 70% of CESC-based workload migrated to Supplier's new primary data center | PDC-09 | VITA negotiates migration date and scope with Agency and approves the final migration timeline and run book. VITA and Agencies provide resources to participate in migration activities, including governance, planning, application analysis, review and approval of deliverables, migration simulations, and other activities as needed. VITA and Agencies create the user acceptance plan and execute acceptance plan after workload migration. | Accept. Migrations cannot be completed without VITA and/or Agency dependencies. Timeline will extend until provided | Testing confirms that all planned migrations have been completed successfully. Legacy environment decommissioned as applicable. CMDB, reporting, and billing records updated. |  | 2021-05-14
11 | PDC-11 | Migration | 100% Workload Migrated | 100% of CESC-based workload migrated to Supplier's new primary data center | PDC-10 | VITA negotiates migration date and scope with Agency and approves the final migration timeline and run book. VITA and Agencies provide resources to participate in migration activities, including governance, planning, application analysis, review and approval of deliverables, migration simulations, and other activities as needed. VITA and Agencies create the user acceptance plan and execute acceptance plan after workload migration. | Accept. Migrations cannot be completed without VITA and/or Agency dependencies. Timeline will extend until provided | Testing confirms that all planned migrations have been completed successfully. Legacy environment decommissioned as applicable. CMDB, reporting, and billing records updated. |  | 2021-08-14
12 | PDC-12 | Reserved
13 | PDC-13 | Reserved
14 | PDC-14 | Reserved
15 | PDC-15 | Migration | Out of the Building | Activities required for exiting the building: - Sanitizing and Disposal of retired assets (both infrastructure and building) | PDC-14 | VITA negotiates migration date and scope with Agency and approves the final migration timeline and run book. VITA and Agencies provide resources to participate in migration activities, including governance, planning, application analysis, review and approval of deliverables, migration simulations, and other activities as needed. VITA and Agencies create the user acceptance plan and execute acceptance plan after workload migration. | Accept. Migrations cannot be completed without VITA and/or Agency dependencies. Timeline will extend until provided | Testing confirms that all planned migrations have been completed successfully. Legacy environment decommissioned as applicable. CMDB, reporting, and billing records updated. |  | 2021-11-14
16 | PDC-16 | Closing | CESC Migration Project Closed | All closing processes have been completed for the project and VITA signoff on the Implementation Project has been received. | PDC-15 | VITA and MSI particpate in Lessons Learned sessions. VITA reviews and signs off on the Implementation. | Continue working to resolve outstanding items. Escalate within governance structures. | Project closure documentation provided, indicating that all necessary migration activities have been completed. | 2021-09-14 | 2021-12-14

## Overview
Overview
This Milestones Exhibit will allow VITA to better understand the key phases, events, and timing of the Supplier's plans.
The worksheet reflects the major events of Supplier's plan for migration of the primary data center. The Milestones will align with other documents as appropriate.
The worksheet is not intended to be a detailed project plan, but rather a list of key milestone activities. The Supplier may add to or delete rows from the worksheet as necessary.
Definitions of Fields
Ref ID # | Unique identifier, to be used at Supplier's option, to tie to other documents (e.g., Implementation Plan, Solution, Critical Deliverables, etc.)
Milestone | Name of the milestone
Category | Name of a grouping of activities (e.g., Service Desk, security) - to be determined at Supplier's option.
Description | Description of the activities comprising the milestone
Dependencies on Other Milestones (Ref #) | Indicate the reference numbers of predecessor/dependent milestones to support the current milestone.
Dependencies (i.e., on Commonwealth or Incumbents) | Describe dependencies or expectations of the incumbent suppliers, VITA, agencies, etc.
Risk Mitigation Approach | Describe the risk mitgation approach for any issues with the dependencies indicated in the prior columns.
Acceptance Criteria | Description of Acceptance Criteria, which will indicate completion of the milestone.
Start Date (Comm +/- Months) | Date when the activity begins in support of the milestone, in Months relative to Commencement.
Due Date (Comm +/- Months) | Date when the milestone will be completed in Months relative to Commencement (i.e. +/- number of months). Fractional values of 0, .25, .5, or .75 may be used.