## Title Page
VA-180815-UC - MOD. 15 | Exhibit 2.4.3 Secondary Data Center Migration Milestones
Exhibit 2.4.3 Secondary Data Center Migration Milestones VA-180815-UC- Modification 15
COMMONWEALTH OF VIRGINIA VIRGINIA IT AGENCY (VITA) SUPPLIER STRATEGY AND PERFORMANCE DIVISION 11751 MEADOWVILLE LANE CHESTER, VIRGINIA 23836

## Secondary DC Milestones
Ref # | Milestone | Category | Milestone Name | Milestone Description | Dependencies on Other Milestones (Ref #) | Dependencies (i.e., on Commonwealth or Incumbents) | Risk Mitigation Approach | Acceptance Criteria | Applicable Rus | Start Date | Due Date
2 | SDC-01 | Infrastruture | Data Center Base Implementation | Secure cage, power and first racks in place. Secondary data center is ready to accept installation of equipment | None | Execution of Contract Mod | Accept. Supplier will execute under the existing Contract with the hosting provider for the primary data center. | Demonstration of completion: Formal notice of milestone completion by Supplier to VITA and copy of notice of completion by SSDC hosting provided provided by Supplier's hosting provider that the implementation of cage, racks an power is complete. | Secured Cage Rack Unit | 2021-09-27 | 2021-12-29
3 | SDC-02 | Infrastructure | Network Core Functional | Data Center LAN core is installed and operational and ready to accept connections from devices in the data center. At least 1 pair of data center interconnects between primary and secondary data centers is active and data can be transmitted between the sites. | SDC-01 | VDN will supply MPLS connections. | Accept. Supplier will implement the LAN core and data center interconnects and routers. Core functionality is not dependant on timing of MPLS or other circits. | Demonstration of completion: Formal notice of mileston completion by Supplier to VITA, demonstrating that data transfer is active between primary and secondary data centers. | IPAM/DNS/DHCP/NTP Appliances Load Balancer Client VPN Lan Base Fee Cross Connects All Data Centers | 2021-11-01 | 2022-02-28
4 | SDC-03 | Infrastructure | SAN Core Functional and SAN Storage is implemented | Redundant, high availability Storage Area Network (SAN) implemented, At least 1 Storage Array is connected to SAN. At least 1 pair of SAN edge switches is connected to core. Compute POD in place with connection to array via SAN. Data can be replicated from array in primary data center to secondary data center. | SDC-02 | None | Not Applicable | Demonstration of completion: Formal notice of mileston completion by Supplier to VITA, demonstrating that data can be replicated from array(s) in primary data center to arrays in secondary data center. |  | 2022-01-03 | 2022-03-28
5 | SDC-04 | Infrastructure | All Private Cloud Operational | All Private Cloud infrastructure is installed and private cloud management and workload domains are implemented. All private cloud is operational and ready to accept virtual machine creation or migration. | SDC-03 |  | Mitigate. Escalate implementation of supporting firewall instratructure. Escalate implemenation of MPLS network connections. | Demonstration of completion: Formal notice of mileston completion by Supplier to VITA, demonstrating that a VM can be implemented at secondary data center or migrated from primary data center. |  | 2022-03-01 | 2022-04-29
6 | SDC-05 | Infrastructure | Secondary Data Center build and migration complete. | Secondary Data Center is operational, all required equipment, data and functions have been migrated from current DR site. | SDC-04 |  | Mitigate. Escalate implementation of supporting STS components. | Demonstration of completion: Formal notice of mileston completion by Supplier to VITA, demonstrating that servers are functional in new data center, All servers in existing DR site turned down. |  | 2022-05-01 | 2022-06-30
7 | SDC-06 | Closing | Exit Current DR Site in Manassas | All equipment has been removed from the existing DR site and site returned to contracted state. Contract with current DR site has been terminated | SDC05 | All infrastructure from the existing DR site removed. | Mitigate. VITA and MSI to Escalate removal of STS & 3rd Party equipment. If necessary, Supplier will receive VITA approval to relocate equipment to another site for storage or disposal | Demonstration of completion: Formal notice of mileston completion by Supplier to VITA; project closure documentation provided indicating that all necessary migration activities have been completed. |  | 2022-07-01 | 2022-07-31
Notes | 1 | Applicable Resource Units will be billable as of the milestone acceptance date for documented quantities. Source of measurment as defined in Exhibit 4.2 - Resource Unit Definitions.
| 2 | The billing start date for data center Resource Units listed will be the later of the implemenation date or the milestone completion date.
| 3 | This contract mod does not add any new or modified Monthly Resource Units

## Overview
Overview
This Milestones Exhibit will allow VITA to better understand the key phases, events, and timing of the Supplier's plans.
The worksheet reflects the major events of Supplier's plan for implementation of Secondary Data Center including any required migration of equipment and/or functionality from the existing DR site. The Milestones will align with other documents as appropriate.
The worksheet is not intended to be a detailed project plan, but rather a list of key milestone activities. The Supplier may add to or delete rows from the worksheet as necessary.
Definitions of Fields
Ref ID # | Unique identifier, to be used at Supplier's option, to tie to other documents (e.g., Implementation Plan, Solution, Critical Deliverables, etc.)
Milestone | Name of the milestone
Category | Name of a grouping of activities (e.g., Service Desk, security) - to be determined at Supplier's option.
Description | Description of the activities comprising the milestone
Dependencies on Other Milestones (Ref #) | Indicate the reference numbers of predecessor/dependent milestones to support the current milestone.
Dependencies (i.e., on Commonwealth or Incumbents) | Describe dependencies or expectations of the incumbent suppliers, VITA, agencies, etc.
Risk Mitigation Approach | Describe the risk mitgation approach for any issues with the dependencies indicated in the prior columns.
Acceptance Criteria | Description of Acceptance Criteria, which will indicate completion of the milestone.
Start Date (Comm +/- Months) | Date when the activity begins in support of the milestone, estimate timeline to meet DR site move-out target.
Due Date (Comm +/- Months) | Date when the milestone will be completed, estimated based on start and elapsed time.