## Title Page
VA-180915-IBTL - MOD. 3: End User Services-Computing | Exhibit 2.4.1 Implementation Milestones
Exhibit 2.4.1 - MOD. 3 Implementation Milestones VA-180915-IBTL: End User Services-Computing
COMMONWEALTH OF VIRGINIA VIRGINIA INFORMATION TECHNOLOGIES AGENCY (VITA) SUPPLY CHAIN MANAGEMENT DIVISION 11751 MEADOWVILLE LANE CHESTER, VIRGINIA 23836

## Overview
Overview
This Milestones Exhibit will allow VITA to better understand the key phases, events, and timing of the Supplier's plans.
The worksheet reflects the major events of Supplier's contract lifecycle, including the Implementation Plan for implementing the Services and ongoing programs for maintaining and updating the Services, with verifiable criteria for acceptance. Milestones reflect the key events indicated over the course of the Implementation Plan and the overall term of Supplier's agreement. The Milestones will align with other documents as appropriate.
The worksheet is not intended to be a detailed project plan, but rather a list of key milestone activities. The Supplier may add to or delete rows from the worksheet as necessary.
Definitions of Fields
Ref ID # | Unique identifier, to be used at Supplier's option, to tie to other documents (e.g., Implementation Plan, Solution, Critical Deliverables, etc.)
Milestone | Name of the milestone
Category | Name of a grouping of activities (e.g., Service Desk, security) - to be determined at Supplier's option.
Description | Description of the activities comprising the milestone
Dependencies on Other Milestones (Ref #) | Indicate the reference numbers of predecessor/dependent milestones to support the current milestone.
Dependencies (i.e., on Commonwealth or Incumbents) | Describe dependencies or expectations of the incumbent suppliers, VITA, agencies, etc.
Risk Mitigation Approach | Describe the risk mitgation approach for any issues with the dependencies indicated in the prior columns.
Acceptance Criteria | Description of Acceptance Criteria, which will indicate completion of the milestone.
Start Date (Comm +/- Months) | Date when the activity begins in support of the milestone, in Months relative to Commencement.
Due Date (Comm +/- Months) | Date when the milestone will be completed in Months relative to Commencement (i.e. +/- number of months). Fractional values of 0, .25, .5, or .75 may be used.

## Implementation Milestones
Ref # | Milestone | Category | Description | Dependencies on Other Milestones (Ref #) | Dependencies (i.e., on Commonwealth or Incumbents) | Risk Mitigation Approach | Acceptance Criteria | Due Date (Comm +/- Months)
EUS-001 | Integrated planning complete | Project Planning | This milestone confirms the supplier has developed their project management plan and that their plan has been integrated their plan into the MSI Implementation Plan. This plan will track the overall schedule and performance to plan, coordinate change activities, identify contention for Commonwealth resources (agency time and VITA time), identify contention for Incumbent resources, manage dependencies between/among Suppliers, manage communication to agencies and stakeholders, manage program risks and issues, identifies lines of communications, map orgranizational charts between supplier and MSI, and activities around SLA / OLA development. | None. |  |  | VITA accepts the deliverables: 3.1 - Services Detailed Implementation Plan; Project Management Plan. | Effective Date + 30 Days
EUS-002 | Knowledge Transfer complete | Personnel | This milestone confirms all knowledge transfer (KT) between supplier and incumbent has been completed. KT activities included but are not limited to meetings with incumbent staff, shadowing, observations of incumbent performing duties. | EUS-0001 |  | Iron Bow has hired Incumbent Managers to assist in identification of qualified resources/incumbent staff, assist in Knowledge Transfer, and stand up of facilities | VITA accepts that all Knowledge Transfer activities have been completed. | 2018-11-30
EUS-003 | Asset discovery and transfer complete | Incumbent Asset Transfer | This milestone confirms titles have been transferred. | EUS-0001 |  |  | VITA accepts the following deliverables: - 3.7 Complete Asset Inventory and CMDB Data Population. In addition, title transferred to supplier for this milestone to be achieved. | 2018-12-15
EUS-004 | Process (SMM) Integration – Draft complete | SMM Development | This milestone confirms that the Service Management Manual development has been initiated as required by supplier by VITA and the MSI. | EUS-0001 |  |  | VITA accepts the following deliverables: - 3.3.1 Service Management Manual - Initial Draft. | 2018-10-30
EUS-005 | Process (SMM) Integration – Final complete | SMM Development | This milestone confirms that all activities required by supplier by VITA and MSI for the development of the Service Management Manual have been completed and has been accepted by VITA and the MSI. | EUS-0001, EUS-0004 |  |  | VITA accepts the following deliverables: - 3.3.2 Service Management Manual - Final Draft. In addition, Operational Level Agreements should be finalized with approval from VITA. | 2018-12-05
EUS-006 | Technology Infrastructure Readiness | Technology Infrastructure | This milestone confirms the suppliers IT infrastructure has been installed, tested sucessfully, and has been implemented succesfully into the environment based on VITA's approval. | EUS-0001 |  | We have more than 30 years experience, SME's in this area, and reachback to the OEM's to mitigate risk Iron Bow has a dedicated team to spearhead the implementation that incldues consulting support from our ITSM provider. This is dedicated consulting support that we can levarage to complete this activity. | VITA accepts the following deliverables - 3.5 Initial Technology Plan; 3.6 Intitial Security Plan - and the completion of the following tasks: Installation and deployment of Hyperconverged Infrastructure to Support Cherwell and SCCM; Software Distribution System Implemented (SCCM); Client Engineering / Patching and Updating Process Established; Hardware Acceptance Testing Completed; Cherwell Service Management System Requirements Defined; Software Test Lab in place; Imaging Test lab in place; New Project Requests and New Work Order Requests; Ongoing Projects and Ongoing Work Orders; Invoice/Billing Requirements Established, Service Desk & Scripts Automation. | 2018-11-15
EUS-007 | Cross Functional (MSI) Integration Complete | MSI Integration | This milestone confirms the suppliers tools have been integrated with the tools contained in the SMS. | EUS-0001, EUS-0006 |  | Iron Bow has a dedicated Team to work with the MSI | VITA accepts the following deliverables: - 3.9 Service Management Systems Integration - and the completion of the following tasks: Cherwell Service Management System Integration (Integration with MSI Tools); MSI Tool Training; Service Catalog Establishment and Integration; Identity and Access Management Requirements. | 2018-11-15
EUS-008 | Personnel Readiness | Personnel | This milestone confirms all required hiring, onboarding, badging, security clearances, and training is completed for the core Iron Bow staff. | EUS-0001, EUS-0002 |  | Iron Bow has hired Incumbent Managers to assist in identification of qualified resources/incumbent staff, assist in Knowledge Transfer, and stand up of facilities | VITA accepts the following tasks have been completed: Incumbent staff contingent offers; Hired and onboarded of all staff; Badging of all Supplier staff; Obtained Security Clearances for all staff; Personnel Gap Assessment; Training of all Supplier staff; Purchases of support SW/HW for all Supplier staff; Local Facility Move-In. | 2018-11-15
EUS-009 | Operational Readiness Complete | Operational Readiness | This milestone confirms the suppliers implementation is complete, it's solution is in place, and is ready to move into operations. | EUS-0001, EUS-0002, EUS-0003, EUS-0004, EUS-0005, EUS-0006, EUS-0007, EUS-0008 |  | We have a dedicated Transition Team with incumbent leadership that will help prepare our team to ensure we can execute Service Takeover in a timely and efficient manner. | VITA accepts the following deliverables: - 3.8 Service Catalog Request and Fulfillment Implementation ; 3.2 Services Implementation Readiness Plan; 3.4 Service Performance and Reporting; Transition Readiness Review; Operational Readiness Review; Commencement of Services. | 2018-12-15
EUS-010 | Asset Integration Complete | CMDB Integration | This milestone confirms complete integration of all software and hardware components into the CMS/CMDB via an electronic interfacing process as outlined in the Contract Implementation Plan. | EUS-007 |  |  | For three agencies (to be provided to STS and SAIC by VITA upon STS submission of completion of the CMDB hardware and separately software integrations) Supplier and SAIC to provide all mapped data (hardware and separately software) to VITA in either .csv, .dat, .txt or .xlsx format and include file headers. The data must be provided within 24 hours of receiving the names of the three agencies. A comparison of the data must result in STS meeting the 95% expected SLA threshold. | 2020-07-01