## Title Page
VA-210517-NTT: Messaging Services | Exhibit 2.6: Current and Planned Projects
Exhibit 2.6 Current and Planned Projects Effective June 11, 2021 VA-210517-NTT - Messaging Services
COMMONWEALTH OF VIRGINIA VIRGINIA IT AGENCY (VITA) SUPPLIER STRATEGY AND PERFORMANCE DIVISION 11751 MEADOWVILLE LANE CHESTER, VIRGINIA 23836

## Intro and Definitions
Current and Planned Projects
Projects fall into three categories including:
* Request for Solution (RFS)
* Commonwealth Project
* Project from Ongoing Programs
Solution Requests | An RFS requires requirements assessment, proposal development and implementation. An RFS is requested by the Customer via the Service Catalog. The MSI manages the demand phase, which includes the solution development process and provides an integrated solution to the Customer. Once the customer approves the solution and pricing, The resulting project may be managed by the MSI or by a single Supplier. The list provided is a snapshot of the current in-flight RFS demands (solutioning is in progress) and projects (solution has been approved and is in implementation).
Commonwealth Projects | Commonwealth projects provide applications and services to support the mission. These projects are initiated and managed by Customer agencies. VITA has an oversight role. Supplier may support these projects where infrastructure is needed and must recognize the schedule and impact of such projects.
Ongoing Programs | Ongoing Programs are defined in the requirements exhibits and may require projects to be initiated and managed. Refresh and Software Currency is currently managed as a program managed by the MSI and under platform oversight. Suppliers are required to initiate projects for refresh and currency efforts.

## RFS Demands
RFS Demands
Note: Extract date May 11, 2021
Demand ID | Demand Name | Request Description | Status | Major IT Project | Customer Requested Production Date | Request Receipt Date | Proposal Delivered to Customer | Forecasted Completion Date | (Proposed) Cost One Time | (Proposed) Cost Recurring
DMND0005074 | SPtoModern | We want to have WCS upgrade our classic SharePoint sites to Modern via script. Please provide information on how long this would take, any issues involved, and any costs associated with such. | Pre-qualification review by WCS |  | 2021-06-21 | 2021-05-04
DMND0005027 | DVS State Approving Agency | The State Approving Agency has a need to exchange documents with external educational institutes. The sharepoint site is public facing. The site should be managed by three different roles. i) Educational Institutes: 1) There are around 500 Institutes that will be uploading documents to this site. 2) Each institute should be allowed to see the documents they uploaded. They should not be able to view other institutes documents. 3) Once uploaded, they cannot delete the documents 4) They should be able to download their own documents whenever they need ii) SAA Staff: 1) Should be able to view all the documents uploaded by educational institutes 2) They should be able to upload and download documents 3) Once uploaded, they should be able to delete the documents iii) SAA Admin: 1) Should be able to view all documents 2) SAA Admin should have ability to delete documents. 3) Should be able to add new institutes, grant access to new accounts and remove access We need to send invitations to the current institutes inviting them to create accounts in the sharepoint site. | Pre-qualification review by WCS |  | 2021-05-19 | 2021-04-26

## RFS Projects
RFS Projects
Note: Extract date May 11, 2021
Project ID | Project Name | Project Description | Project Status | Major IT Project | Actual Start Date | Planned Completion Date | Managed by
PRJ0010441 | Data Center Relocation Program (DCRP) - MSI -Data Center Move | *Supporting Moving VITA Datacenters and migrating to cloud. | Active | Yes | 2019-08-19 08:00 | 2022-03-31 12:00 | SAIC - 8803
PRJ0011418 | DCRP – Tempus Nova | Please provide the hours needed by Tempus Nova to build their test plans and to execute them after their applications have been migrated to the new data center at QTS | Active |  | 2020-03-20 08:00 | 2021-06-30 17:00 | TNV - 8804
PRJ0011863 | eMail address for eBiz application | We have Oracle eBusiness Application iExpense and it requires to receive an email from DSS users for approvals on Linux Server. We have this application on four servers with unique user on each server. We need to set up these system accounts in mail server so it can receive the e-mail. | Active |  |  | 2021-05-28 17:00 | TNV - 8804
PRJ0012030 | OneDrive for WCS | SPLM request to modify SharePoint Online/Teams to include OneDrive for storage. OneDrive will show up as a storage option in Teams. We have been working with AvePoint to identify and remediate the sharing of files between agencies. We are updating the existing SharePoint VAR to include OneDrive. This service will see the modification of the Workplace Collaboration Service to include OneDrive for storage. At adoption of the service, OneDrive will show up as a storage option in Microsoft Teams. | Active |  | 2021-04-28 08:00 | 2021-06-11 17:00 | SAIC - 8803
PRJ0011174 | VDOT - WCS - SPOL -Migration-rev | Provision WCS Migration Services to migrate Customer’s existing Windows Server 2010 SharePoint data to the proposed Suppliers’ SharePoint Online Service instance and to Office 365. Suppliers will migrate up to 8,000 Customer-users | Active |  | 2020-03-31 08:00 | 2021-08-06 17:00 | SAIC - 8803
PRJ0011640 | WCS Consulting Services - DGS SharePoint Administration Support Project | Tier 2 SharePoint Administration using Workforce Collaboration Services Consulting Services - 12-months of on-call support 7am-7pm Monday-Friday | Active |  | 2020-12-10 08:00 | 2020-12-10 17:00 | VITA - WCS
*Supporting indicates that the supplier may be involved but is not the lead STS managing the project

## Ongoing Programs
Ongoing Programs
(These programs are currently not supported by the incumbent supplier. The new Messaging supplier will be expected to support them as agreed to in Ex 3.1)
Service Management Manual Currency
Technology Planning
ITISP Measures
Disaster Recovery Preparedness
Security Program (There is some activity that is ongoing related to this in the Messaging tower, however it is being headed up by the Managed security supplier)
Risk Management Program
Refresh and Software Currency
AirWatch MDM Support
IronPort Appliance Support
Listsrv Support
Audit support
Google License harvesting and reconciliation