## Title Page
VA-240322-PSLI - Mainframe Services - MOD. 4 | Exhibit 2.4.1: Implementation Milestones
Exhibit: 2.4.1 - MOD. 4 Implementation Milestones
Effective October 15, 2024
VA-240322-PSLI - Mainframe Services
COMMONWEALTH OF VIRGINIA
VIRGINIA IT AGENCY
SUPPLIER STRATEGY AND PERFORMANCE DIVISION
7325 BEAUFONT SPRINGS DR.
RICHMOND, VA, 23225

## Introduction
VA-240322-PSLI - Mainframe Services - MOD. 4
INTRODUCTION
This Exhibit 2.4.1 (Implementation Milestones) sets forth the following:
Implementation Milestones
- the reference number, name, and description of each Implementation Milestone and One-Time Deliverable (OTD),
- the dependencies (Integration Points, OTDs, and Milestones) which must be accepted by VITA before Supplier may submit the Milestone or OTD for approval,
- the Acceptance Criteria that Supplier must meet in order for VITA to accept the Milestone or OTD as set forth in Article 10 Deliverables of the Agreement,
- the timing regarding the submission of select Milestones and OTDs, and
- a column for Supplier Comments regarding the Milestone or OTD

## Implementation Milestones
Implementation Milestones
| Ref # | Milestone | Description | Dependencies | Deliverable Acceptance Criteria | Due Date | Supplier Comments
| M-01 | Transition Kick off (Project Planning Workshop) | Hold kick-off meeting with VITA Stakeholders & Project Team Members |  | Gate Review—VITA accepts meeting schedule, Client kickoff held, and attendance is recorded | 2024-04-15 | Target Effect Date + 2 weeks
| OTD 3.1 | Services Detailed Implementation Plan | Supplier has successfully delivered a project management plan that has been integrated and coordinated with VITA and the Customers. This plan will track the overall schedule and performance to plan, coordinate change activities, identify contention for resources, identify contention for Incumbent resources, manage dependencies between/among Suppliers, manage communication to agencies and stakeholders, manage program risks and issues, identifies lines of communications, and map organizational charts between supplier and MSI. | Integration Points: - #1: Implementation Plan Integration - #2: Organizational Mapping and Integration -#3: Incumbent and Current Staff Retention | 1) VITA and the Customers accept the Integrated Project Management Plan. 2) VITA accepts Supplier's Communication Management Plan. 3) VITA accepts Supplier's Quality Management Plan. 4) VITA accepts Supplier's Organizational Change Management Plan. | 4/29/2024 | Target Effect Date + 4 weeks
| OTD 3.2 | Services Implementation Readiness Plan | Supplier has successfully delivered a written plan and checklist that details all activities and assigned owners required to a) implement the Services, b) complete the successful transition of obligations to the Supplier, and c) communicate the new services to the COV customer base. | Integration Points: - #19: Communications Plan | 1) VITA accepts Supplier's Services Implementation Readiness Plan. 2) VITA accepts Supplier's Services Implementation Readiness Checklist. 3) VITA Communications and Business Readiness accept the Services Implementation Communication Plan. | 2024-04-29 | Target Effect Date + 4 weeks
| OTD 3.3.1 | Process (SMM) Integration Initial Draft | Supplier has successfully delivered all initial content and details required by VITA for the development of the Service Management Manual (SMM), and has successfully incorporated them into the draft document. | Integration Point: - #5: Initial Service Management Manual Development | VITA accepts, and VITA approves, all required SMM chapters. | 2024-05-13 | Target Effect Date + 6 weeks
| OTD 3.4 | Service Performance and Reporting | Supplier has agreed to and is able to report and operate by the SLAs in their respective contract in accordance with Exhibit 3.1 (Service Level Matrix) |  | VITA and the Customers accept Supplier Reports and SLAs Artifact(s): - All SLA reports are submitted and approved in the SMS or as agreed to by VITA. | 5/28/2024 | Commencement - 1 week
| OTD 3.5 | Initial Security Plan | Supplier has successfully delivered an initial draft of the System Security Plan. |  | VITA CSRM accepts the Initial System Security Plan (SSP). | 5/13/2024 | Target Effect Date + 6 weeks
| OTD 3.7 | Complete Asset Inventory and CMDB Population | Supplier has successfully delivered the full asset inventory, and has successfully designed, implemented, and populated their CMDB record(s). |  | 1) VITA and the Customers accept Supplier's Asset Inventory. 2) VITA and the Customers accept Supplier's CMDB design, implementation, population, and true-up. | 5/13/2024 | Target Effect Date + 6 weeks
| OTD 3.8 | Service Catalog Request and Fulfillment Implementation | Supplier has successfully delivered service catalog updates that includes functionality to provision all services with approval chains in accordance with the SMM. | Integration Point: - #14: Catalog Integration | 1) MSI, VITA and the Customers accept Supplier's Service Catalog updates. 2) VITA and the Customers accept Supplier's Service Catalog design, provisioning, implementation, functionality, approval chain, and population. | 2024-05-28 | Commencement - 1 week
| OTD-3.9 | Service Management Systems (SMS) Implementation | Supplier’s tools have been successfully integrated with the tools contained in the SMS. | Integration Points: - #6: SMS - Tools Integration - OTD 3.8 - Service Catalog Request and Fulfillment Implementation | 1) VITA and the Customers accept that Supplier's tools are fully appropriately integrated with SMS, have been successfully tested, and are live in the production environment. 2) VITA and the Customers accept that Supplier has completed all necessary updates to CMDB record(s) and has processes in place to maintain the CMDB record(s). | 2024-05-28 | Commencement - 1 week
| OTD 3.10.1 | Operating Level Agreements - Initial Draft | OLAs are agreed on between STS and Supplier, MSI and Supplier, and where necessary, OLAs have been agreed to between Supplier and other Suppliers in the multi-sourcing environment. |  | 1) Written acceptance by all parties confirming that their agreement w/ all Draft OLAs. 2) VITA accepts all Completed draft OLAs. 3) VITA and Customers Accept that the framework and components of the submitted documentation are compliant with current VITA SMMs and are ready for PAG review. 4) VITA and MSI Accept that the framework and components of the submitted documentation are compliant with current VITA SMMs and are ready for PAG review. | 5/13/2024 | Target Effect Date + 6 weeks
| OTD 3.11 | SAM Reconciliation | Software Asset Management (SAM) and SAM Data Population is complete. Working with VITA and the Customers, the supplier will populate all applicable services into the Supplier's Software Asset Management Application (SAM) |  | Supplier will provide a complete inventory of licensed user to license type. Artifacts: 1) Report showing services of each user and licensed software assigned. 2) Report providing detail on licenses owned (rights) compared to licenses consumed (entitlements) | 2024-05-20 | Commencement - 2 weeks
| M-02 | Governance/ SMM/ OLA Initial Documentation Acceptance | Supplier and the Customers have established a governance framework and Supplier has identified appropriate personnel to attend governance forums | Integration Points: - #7: Governance - #8: SLA/OLA Development OTDs: - OTD 3.1 - Services Detailed Implementation Plan - OTD 3.3.1 - Service Management Manual Initial draft - OTD 3.4 - Service Performance and Reporting | 1) VITA and the Customers accept Supplier's governance framework. 2) VITA accepts Supplier's identified appropriate personnel to attend governance forums and adhere to overall Governance standards. | 5/28/2024 | Commencement - 1 week
| M-03 | Initial Design Acceptance | Supplier has submitted and received approval for all VITA Holistic Architecture Review (HARP) documentation and the System Security Plan. | OTDs: - OTD 3.5 - Initial Security Plan | 1) VITA Enterprise Architecture and the Customers accept the following HARP components: a) High Level Section (HLS) b) Detailed Design Section (DDS) c) As Built Documentation (ASB) | 2024-05-28 | Commencement - 1 week Assumes Target Effect Date and Implementation kickoff
| M-04 | Asset Discovery and Transfer | Titles have been transferred from Incumbent Supplier to the appropriate parties. | Integration Point: - #9: Asset Discovery and Transfer OTDs: - OTD 3.7 - Complete Asset Inventory and CMDB Population - OTD 3.11 - SAM Reconciliation | VITA accepts that all software titles listed in Exhibit 4.7 have been transferred and/or updated to VITA, Supplier, or other appropriate parties. Artifact(s): - Documentation certifying that all software titles listed in Exhibit 4.7 have been transferred appropriately. | 2024-05-28 | Assumes Target Effect Date and Implementation kickoff Hardware asset transfer is NA, Software transfer final dispositions will be applicable
| M-05 | Commencement Readiness | Supplier is ready to Commence Services. This includes, at a minimum, the following: 1) All required hiring, onboarding, badging, security clearances, and training is complete, 2) All titles, licenses, and accesses have been transferred, and 3) Supplier’s implementation is complete, their solution is fully in place, and they are ready to assume operations from Incumbent Supplier and commence services | Integration Points: - OTD 3.2 - Services Implementation Readiness Plan - OTD 3.9 - Service Management Systems (SMS) – Tools - OTD 3.10.2 = Operating Level Agreements, Final - M-01 - Transition Kickoff - M-02 - Initial Documentation Acceptance - M-03 - Initial Design Acceptance - M-04 - Asset Discovery and Transfer | 1) VITA accepts Supplier's Personnel readiness. This will include, at a minimum: a) Incumbent staff contingent offers b) Hired, onboarded, and badged all Supplier staff c) Obtained Security Clearances for all Supplier staff d) Trained of all Supplier staff e) Provisioned support SW/HW for all Supplier staff f) Provisioned appropriate access for all Supplier staff g) Personnel Gap Assessment h) Local Supplier Facility Move-In (if applicable) 2) VITA accepts Supplier's readiness to commence services. | 2024-05-28 | Commencement - 1 week Assumes Target Effect Date and Implementation kickoff
| M-06 | Commencement Date | Supplier successfully assumes full operational responsibility and commences service delivery. | Milestones: - M-05 - Commencement Readiness | VITA accepts Supplier's successful Commencement of Services based on successful completion of Transition Plan and written VITA Acceptance of transition related Deliverables and milestones. | 2024-06-01
| OTD 3.3.2 | Process (SMM) Integration - Final | All activities required of Supplier for the development of the Service Management Manual have been successfully completed and accepted by VITA and the Customers. | OTDs: - OTD 3.3.1 - Process (SMM) Integration Initial Draft | 1) PAG has approved Supplier's SMM for each process cited in their contract exhibits. For shared and cross-functional processes, supplier will comply with the existing SMMs as applicable. 2) VITA accepts all Supplier SMMs. | 2024-05-28 | Commencement - 1 week Assumes Target Effect Date and Implementation kickoff
| OTD 3.10.2 | Operating Level Agreements - Final | OLAs are agreed on between STS and Supplier, and where necessary, OLAs have been agreed to between Supplier and other Suppliers in the multi-sourcing environment. | OTDs: - OTD 3.10.1 - Operating Level Agreements - Initial Draft | 1) PAG has approved all Supplier OLAs, and all applicable parties have executed them. | 2024-05-28 | Commencement - 1 week Assumes Target Effect Date and Implementation kickoff
Post-Commencement Implementation & Transition Milestones
| OTD 3.14 | Transition Closure Report | Supplier has completed all Implementation and Transition Project activities and has successfully delivered a comprehensive Implementation and Transition Closure Report |  | VITA accepts Supplier's Closure Report. | 2024-07-03 | Commencement + 4 weeks Assumes Target Effect Date and implementation kickoff
| M-07 | Transition Closure | Supplier has: 1) Assumed full operational responsibility 2) Commenced Services 3) Completed Steady-State handover 4) Fully offboarded Incumbent Supplier from the environment 5) Demonstrated how all contractual requirements have been met 6) Completed Project closeout | All Integration Points. All OTDs. All preceding Milestones. | 1) Gate Review: VITA accepts project closure as per Agreement 2) VITA approves Supplier Implementation and Transition project team disengagement | 2024-07-03 | Commencement + 4 weeks Assumes Target Effect Date and implementation kickoff
| M-08 | Mainframe and Storage Refresh Cutover | Supplier will install and move production workload to new Mainframe CPU and storage hardware platforms. |  | Supplier completes succesful cutover to Mainframe CPU and Storage hardware and all stakeholders accept the environment into production status | 12/16/2024 | Commencement Date + 4-5 Months (or as otherwise mutually agreed to by the Parties)
| M-09 | Circuit Geographic Diversity - Mid-Atlantic Data Center (MDC) | Complete carrier provisioning of diverse MPLS circuits at Peraton Mid-Atlantic Data Center in Clarksville, VA |  | VITA accepts supplier's submission of evidence of carrier completion of provisioning. | 2024-07-22 | Commencement Date + 2 Months (or as otherwise mutually agreed to by the Parties)
| M-10 | SMF Log Conversion for MSS SIEM | Install and configure required tools on Mainframe to extract and deliver SMF log events to the MSS SIEM. |  | VITA accepts suppliers' test plan results confirming delivery of SMF log events to the MSS SIEM. | 10/29/2024 | Commencement Date + 1 Month (or as otherwise mutually agreed to by the Parties)
* All Due Dates in Column G will be finalized between the Parties (using the Supplier's comments field in Column H as an initial guide), prior to or during to M-01 Transition Kick Off ensuring that all Implementation Milestone Due Dates support and ensure M-06 (Commencement Date) as 06/01/2024.