## Title Page
VA-240920-NTT: Managed Public Cloud Services - Mod-1 | Exhibit 2.4.1: Implementation Milestones
Exhibit: 2.4.1
Implementation Milestones
VA-240920-NTT: Managed Public Cloud Services
COMMONWEALTH OF VIRGINIA
VIRGINIA IT AGENCY
SUPPLY CHAIN MANAGEMENT
7325 BEAUFONT SPRINGS DR.
RICHMOND, VA, 23225

## Introduction
VA-240920-NTT: Managed Public Cloud Services
INTRODUCTION
This Exhibit 2.4.1 (Implementation Milestones) sets forth the following:
Implementation Milestones
- the reference number, name, and description of each Implementation Milestone and One-Time Deliverable (OTD),
- the dependencies (Integration Points, OTDs, and Milestones) which must be accepted by VITA before Supplier may submit the Milestone or OTD for approval,
- the Acceptance Critieria that Supplier must meet in order for VITA to accept the Milestone or OTD,
- the timing regarding the submission of select Milestones and OTDs, and
- a column for Supplier Comments regarding the Milestone or OTD

## Implementation Milestones
Implementation Milestones
Ref # | Name | Description | Dependencies | Acceptance Criteria | Revised Due Date | Supplier Comments
M-01 | Transition Kick off (Project Planning Workshop) | Hold kick-off meeting with VITA Stakeholders & Project Team Members |  | Gate Review—VITA accepts meeting schedule, Client kickoff held, and attendance is recorded | 2024-10-22 | Kick-off held on 10/22/2024 and considered as Day 1 of Transition.
OTD 3.1 | Services Detailed Implementation Plan | Supplier has successfully delivered a project management plan that has been integrated and coordinated with VITA, MSI, the Incumbent, and all applicable Service Towers. This plan will track the overall schedule and performance to plan, coordinate change activities, identify contention for resources, identify contention for Incumbent resources, manage dependencies between/among Suppliers, manage communication to agencies and stakeholders, manage program risks and issues, identifies lines of communications, and map organizational charts between supplier and MSI. | Integration Points: - #1: Implementation Plan Integration - #2: Organizational Mapping and Integration | 1) VITA and the MSI accept the Integrated Project Management Plan. 2) VITA accepts Supplier's Communication Management Plan. 3) VITA accepts Supplier's Quality Management Plan. 4) VITA accepts Supplier's Organizational Change Management Plan. | 12/20/2024 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner. VITA acceptance date depends on VITA review and approval of the dependencies.
OTD 3.2 | Services Implementation Readiness Plan | Supplier has successfully delivered a written plan and checklist that details all activities and assigned owners required to a) implement the Services, b) complete the successful transition of obligations to the Supplier, and c) communicate the new services to the COV customer base. | Integration Points: - #19: Communications Plan | 1) VITA accepts Supplier's Services Implementation Readiness Plan. 2) VITA accepts Supplier's Services Implementation Readiness Checklist. 3) VITA Communications and Business Readiness accept the Services Implementation Communication Plan. | 2024-12-20 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner. VITA acceptance date depends on VITA review and approval of the dependencies.
OTD 3.3.1 | Process (SMM) Integration - Initial Draft | Supplier has successfully delivered all initial content and details required by VITA and the MSI for the development of the Service Management Manual (SMM), and has successfully incorporated them into the draft document. | Integration Point: - #5: Initial Service Management Manual Development | VITA and the MSI accept, and VITA approves, all required SMM chapters. | 2024-12-27 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner. VITA acceptance date depends on VITA review and approval of the dependencies.
OTD 3.4 | Service Performance and Reporting | Supplier has agreed to and is able to operate by the SLAs in their respective contract. |  | VITA and the MSI accept Supplier SLAs Artifact(s): - All SLA reports are submitted and approved in MSI SMS | 2025-02-21 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner.
OTD 3.5 | Initial Security Plan | Supplier has successfully delivered an initial draft of the System Security Plan |  | VITA CSRM accepts the Initial System Security Plan (SSP). | 2025-02-07 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner.
OTD 3.7 | Complete Asset Inventory and CMDB Population | Supplier has successfully delivered the full asset inventory, and has successfully designed, implemented, and populated their CMDB record(s). |  | 1) VITA and the MSI accept Supplier's Asset Inventory. 2) VITA and the MSI accept Supplier's CMDB design, implemenetation, population, and true-up. | 2025-03-14 | Delivery dates are dependent upon MSI providing resources and information requested by supplier in a timely manner. CMDB population requires new NTT DATA CMDB running in production.
OTD-3.9 | Service Management Systems (SMS) – Tools Integration | Supplier’s tools have been successfully integrated with the tools contained in the SMS. This also includes integration of all software and hardware components into the CMS/CMDB via an electronic interfacing process. This milestone also confirms that the supplier has integrated their solution into the MSI's CBTI solution and has incorporated the applicable tagging standard. It also confirms that the supplier has integrated into the Managed Security Suppliers toolsets as applicable. | Integration Points: - #6: SMS - Tools Integration - #15: Identity and Access Management Requirements | 1) VITA and the MSI accept that Supplier's tools are fully integrated with MSI SMS, have been successfully tested, and are live in the production environment. 2) VITA and the MSI accept that Supplier has completed all necessary updates to CMDB record(s) and has processes in place to maintain the CMDB record(s). 3) VITA and the MSI accept that Supplier's tools are fully integrated with the CBTI, have been successfully tested, and are live in the environment. 4) VITA and the MSI accept that Supplier's tools are fully integrated with the MSS' toolsets, have been successfully tested, and are live in the production environment. | 2025-03-07 | Delivery dates are dependent upon MSI providing resources and information requested by supplier in a timely manner. Acceptance Criteria #2 - Any new NTT DATA tools will be integrated into the KSE test environment, so as to not interfere with Incumbent's tools and operations. They will be turned on in production on the day of cutover. Suggested language for #2: VITA and the MSI accept that Supplier has completed all necessary updates to test CMDB record(s) and has processes in place to maintain the CMDB record(s).
OTD 3.10.1 | Operating Level Agreements - Initial Draft | OLAs are agreed on between MSI and Supplier, and where necessary, OLAs have been agreed to between Supplier and other Suppliers in the multi-sourcing environment. |  | 1) Written acceptance by all parties confirming their agreement with and intent to abide by all Draft OLAs. 2) VITA accepts all Completed draft OLAs. 3) VITA and MSI Accept that the framework and components of the submitted documentation are compliant with current VITA SMMs and are ready for PAG review. | 2025-01-08 | Delivery dates are dependent upon MSI providing resources and information requested by supplier in a timely manner.
OTD 3.11 | SAM Reconciliation | Software Asset Management (SAM) and SAM Data Population is complete. Working with MSI, the supplier will integrate all applicable services into the MSI SMS Software Asset Management Application (SAM) |  | Supplier will provide a complete inventory of licensed user to license type. Artifacts: a) Report showing services of each user and licensed software assigned. b) Report providing detail on licenses owned (rights) compared to licenses consumed (entitlements) | 2025-03-14 | Delivery dates are dependent upon MSI providing resources and information requested by supplier in a timely manner.
OTD 3.12 | Remediation Plan | Supplier has completed their assessment of the current service environment(s) to identify any issues that may require remediation, has fully documented those issues, and has successfully delivered a remediation plan to address them that meets best practices and Commonwealth requirements. |  | 1) VITA accepts Supplier's assessment of the current service environment(s) and associated identification and documentation of issues requiring remediation. 2) VITA accepts Supplier's Remediation Plan | 2025-02-28 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner.
M-02 | Initial Documentation Acceptance | Supplier and the MSI have established a governance framework and Supplier has identified appropriate personnel to attend governance forums | Integration Points: - #7: Governance - #8: SLA/OLA Development OTDs: - OTD 3.1 - Services Detailed Implementation Plan - OTD 3.3.1 - Service Management Manual Initial draft - OTD 3.4 - Service Performance and Reporting - OTD 3.10.1 - Initial draft OLA’s with MSI | 1) VITA and the MSI accept Supplier's governance framework. 2) VITA accepts Supplier's identified appropriate personnel to attend governance forums and adhere to overall Governance standards. | 2025-02-28 | Delivery dates are dependent upon MSI providing resources and information requested by supplier in a timely manner. NTT Data Delivery date is dependent upon VITA approval of the dependencies.
M-03 | Initial Design Acceptance | Supplier has submitted and received approval for all VITA Holistic Architecture Review (HARP) documentation and the System Security Plan. | OTDs: - OTD 3.5 - Initial Security Plan | 1) VITA Enterprise Architecture and the MSI accept the following HARP components: a) High Level Section (HLS) b) Detailed Design Section (DDS) c) Incumbent As Built Documentation (ASB) | 2025-02-22 | Delivery dates are dependent upon MSI providing resources and information requested by supplier in a timely manner. NTT Data Delivery date is dependent upon VITA approval of the dependencies
M-04 | Asset Discovery and Transfer | Titles have been transferred from Incumbent Supplier to the appropriate parties. | Integration Point: - #9: Asset Discovery and Transfer OTDs: - OTD 3.7 - Complete Asset Inventory and CMDB Population - OTD 3.11 - SAM Reconciliation | VITA accepts that all software titles listed in Exhibit 4.7 have been transferred and/or updated to VITA, Supplier, or other appropriate parties. Artifact(s): - Documentation certifying that all software titles listed in Exhibit 4.7 have been transferred appropriately. | 2025-03-14 | Delivery dates are dependent upon MSI providing resources and information requested by supplier in a timely manner. NTT Data Delivery date is dependent upon VITA approval of the dependencies
M-05 | Commencement Readiness | Supplier is ready to Commence Services. This includes, at a minimum, the following: 1) All required hiring, onboarding, badging, security clearances, and training is complete, 2) All titles, licenses, and accesses have been transferred, and 3) Supplier’s implementation is complete, their solution is fully in place, and they are ready to assume operations from Incumbent Supplier and commence services, | All Integration Points except: - #18: Finalize the Operational Level Agreements OTDs: - OTD 3.2 - Services Implementation Readiness Plan - OTD 3.9 - Service Management Systems (SMS) – Tools Integration - OTD 3.12 - Remediation Plan Milestones: - M-01 - Transition Kickoff - M-02 - Initial Documentation Acceptance - M-03 - Initial Design Acceptance - M-04 - Asset Discovery and Transfer | 1) VITA accepts Supplier's Personnel readiness. This will include, at a minimum: a) Incumbent staff contingent offers b) Hired, onboarded, and badged all Supplier staff c) Obtained Security Clearances for all Supplier staff d) Trained of all Supplier staff e) Provisioned support SW/HW for all Supplier staff f) Provisioned appropriate access for all Supplier staff g) Personnel Gap Assessment h) Local Facility Move-In (if applicable) 2) VITA accepts Supplier's readiness to commence services. | 2025-03-14 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner. NTT Data requires time as per the schedule to shadow the incumbent prior to commencement date when NTT Data takes over Managed Services.
M-06 | Commencement Date | Supplier successfully assumes full operational responsibility and commences service delivery. | Milestones: - M-05 - Commencement Readiness | VITA accepts Supplier's successful Commencement of Services. | 2025-03-14 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner.
OTD 3.3.2 | Process (SMM) Integration - Final | All activities required of Supplier for the development of the Service Management Manual have been successfully completed and accepted by VITA and the MSI. | OTDs: - OTD 3.3.1 - Process (SMM) Integration Initial Draft | 1) PAG has approved Supplier's SMM for each process cited in their contract exhibits. For shared and cross-functional processes, supplier will comply with the existing SMMs as applicable. 2) VITA accepts all Supplier SMMs. | 2025-01-22 | Delivery dates are dependent upon MSI providing resources and information requested by supplier in a timely manner. NTT Data Delivery date at end of month 4 is dependent upon VITA approval of the dependencies.
OTD 3.10.2 | Operating Level Agreements - Final | OLAs are agreed on between MSI and Supplier, and where necessary, OLAs have been agreed to between Supplier and other Suppliers in the multi-sourcing environment. | OTDs: - OTD 3.10.1 - Operating Level Agreements with MSI - Initial Draft | 1) PAG has approved all Supplier OLAs, and all applicable parties have executed them. | 2025-02-28 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner. NTT Data Delivery date is dependent upon VITA approval of the dependencies.
OTD 3.13 | Modernization Plan | Supplier has completed their assessment of the current service environment(s) to identify any modernization opportunities, has fully documented these modernization items, and has successfully delivered a modernization plan to implement them that meets best practices and Commonwealth requirements. |  | 1) VITA accepts Supplier's assessment of the current service environment(s) and associated identification and documentaiton of modernization items. 2) VITA accepts Supplier's Modernization Plan | 2025-02-28 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner. NTT Data Delivery date is dependent upon VITA approval of the dependencies.
OTD 3.14 | Transition Closure Report | Supplier has completed all Implementation and Transition Project activities and has successfully delivered a comprehensive Implementation and Transition Closure Report |  | VITA accepts Supplier's Closure Report. | 2025-03-31 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner.
M-07 | Transition Closure | Supplier has: 1) Assumed full operational responsibility 2) Commenced Services 3) Completed Steady-State handover 4) Fully offboarded Incumbent Supplier from the environment 5) Demonstrated how all contractual requirmeents have been met 6) Completed Project closeout | All Integration Points. All OTDs. All preceding Milestones. | 1) Gate Review: VITA accepts project closure as per Agreement 2) VITA approves Supplier Implementation and Transition project team disengagement | 2025-03-31 | Delivery dates are dependent upon VITA providing resources and information requested by supplier in a timely manner.